## Action Items
| JOINT COUNCILS ACTION ITEMS |  |  |  | Last updated: 05/09/2018
|  | Next Joint Councils Meeting: | September 26, 2018 - Whitehorse, YT
| ACTION ITEM | LEADS | ASSIGNED | STATUS | NOTES
Joint Councils Teleconference of July 30, 2018
#1A | Framework Working Group Co-Chairs to work with ICCS to procure the services of a resource and manage one-year contract. | Natasha Clarke, Sophia Howse & ICCS | 2018-07-30 | Underway | Position (one-year contract) to be filled in October 2018. Recruitment period Aug 28 to Sept 28, 2018.
#1C | Natasha Clarke and Sophia Howse to provide a report to members in fall 2019 regarding the contract position to assess whether or not this has achieved its objectives. | Natasha Clarke, Sophia Howse | 2018-07-30 | Pending | Item scheduled in fall 2019.
#2A | Rhianna Begley and Keleigh Annau to send out to members, via ICCS, a call out for participation for the GDPR group. | Chad Hoskins | 2018-07-30 | Completed | Message sent out via ICCS.
#2B | The GDPR Group to share their Terms of Reference and work plan with members at an upcoming meeting/teleconference. | Chad Hoskins | 2018-07-30 | Pending | Item scheduled in fall 2019.
Joint Councils Teleconference of June 7, 2018
#1B | Research Committee Co-Chairs to provide progress report in fall of 2018 related to longer term funding and other work program elements. | Richard Dalpé, Guy Gordon | 2018-07-06 | Pending | Update scheduled in fall 2018.
#2 | The Death Notification Working Group to report at the Joint Councils in-person meetings in Whitehorse on the: - Design thinking process for the co-development of a Bereavement Bundle Communications Tool and - Roadmap for a Digital “tell-us-once” solution | Anik Dupont, Anne Matthews, Ron Hinshaw | 2018-07-06 | Pending | Item on the September 26th meeting agenda
Joint Councils Teleconference of April 25, 2018
#1 | Digital Identity Working Group Co-Chairs to report back on roadmap of all streams of work at an upcoming teleconference/meeting (refer to per previous action items from the February 2018 meeting). | Jackie Stankey, Sophia Howse | 25/04/2018 | Pending | Item on the September 26th meeting agenda
Joint Councils Meeting of February 21, 2018 (Toronto)
#1A | Framework Working Group: PSCIOC members to discuss at their meeting of Feb 22nd, the recommendation from the FWG to transition the Information Management (IM) Sub-Committee and the Information and Communication Technology Policy Working Group to Communities of Practice. PSCIOC to provide further feedback to the Joint Councils. | PSCIOC Members | 2018-02-21 | Underway | Update scheduled for upcoming teleconference (fall 2018). At the PSCIOC meeting of Feb 22, 2018, members agreed to keep IM Sub-Committee as is and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be assigned to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at their July 23rd teleconference.
#1E (i) | Framework Working Group to develop guideline or "cheat-sheet", for Councils' approval, to help ensure the proper type of group is created, when required. | FWG Leads and ICCS Secretariat | 2018-02-21 | Pending | Document to be tabled at an upcoming Joint Councils teleconference.
#1E (ii) | Framework Working Group to develop governance structure (dashboard) of all working groups of the Councils. | FWG Leads and ICCS Secretariat | 2018-02-21 | Underway | A visual map of the Joint Councils is already available however the secretariat has engaged an external expert in design thinking to improve information management and reporting to the Councils. An infographic of the ecosystem of the Councils will be available in September.
#2A | Digital Strategy: Each jurisdiction to develop their own jurisdictional digital principles and to have this ready for the next in person meeting of September 26th. Members to have a collective review of all digital principles to check for alignment. | Guy Gordon, Mark Burns, Sean McLeish | 2018-02-21 | Pending | Item on the November teleconference
#2B | Digital Strategy: Joint Councils members approved to use the TBS's Digital Principles to guide the work of the Councils and of all working groups and committees. Digital Strategy leads to take the lead on this work and to continue to work with Joint Councils in defining role related to pan-Canadian digital strategy. | Guy Gordon, Mark Burns, Sean McLeish | 2018-02-21 | Pending | Item on the November teleconference
#3C | Canada's Digital Interchange leads (Robert Frelich and Arlene Williams) to report back to the Joint Councils on the CDI pilots at the next in person meeting in the fall. | Robert Frelich, Arlene Williams | 2018-02-21 | Pending | Item on the September 26th meeting agenda
#3D | Digital Identity leads to provide an updated roadmap with timelines (all streams of work including IMSC, CDI, etc) at the next Joint Councils meeting. | Jackie Stankey, Sophia Howse | 2018-02-21 | Pending | Item on the September 26th meeting agenda
#4 | Client Centric Services leads to update Intergovernmental Client-Centric Services Maturity Model with members' feedback from February meeting and to facilitate the development of client-centric project-based initiatives with interested partners. | Bev Dicks, Annette Vermaeten | 2018-02-21 | Pending | Item on the September 26th meeting agenda
#7 | Privacy Sub-Committee to report back to the Joint Councils on request related to information on streamlining privacy impact assessment and connecting the work of this group to the digital identity priority and the work around cybersecurity and cloud working group. | Chad Hoskins | 2018-02-21 | Pending | Update scheduled for fall 2018.
Joint Councils Teleconference of Nov. 17, 2017
#5 | CDI to provide an update on the work of the CDI Benefits Realization Study at the next teleconference. | Robert Frelich, Arlene Williams | 2017-11-17 | Pending | Update scheduled for upcoming teleconference (fall 2018)
#1F | Joint Councils Meeting of February 22, 2017
| Framework Working Group to work on development of a Joint Councils’ Terms of Reference (currently there is only a mandate for PSSDC and PSCIOC) and recommendations on the future of the FWG and accountability of the Councils to the logic model. FWG to provide an update at an upcoming teleconference and/or meeting. | Natasha Clarke, Sophia Howse | 2017-02-22 | Pending | Update scheduled for upcoming teleconference (fall 2018). This work would be undertaken by the new strategic policy analyst (to start in October 2018)

## Decisions
DECISIONS
| ITEM | STATUS
JOINT COUNCILS MEETING OF FEBRUARY 21, 2018
#1 | Framework WG recommendation for the following groups to continue their work - PSSDC's Service Network Collaboration WG, Service to Business CoP, the Joint Councils' Canada's Open Gov WG, IMSC, CDI, DNWG, and the PSCIOC's Cloud WG. Members approved the FWG recommendation. | Approved
#2 | Framework WG recommendation for the work of the PSCIOC's NCSIP and the Joint Councils' Privacy Sub-Cmte and Research Committee to continue and for the Councils to leverage their expertise to advance the JC priorities. | Approved
#3 | Framework WG recommendation to task the PSCIOC's IT Procurement WG with activities related to priorities or transition to CoP: Kathryn Bulko, IT Procurement Chair, welcome suggestions from members on activities that this working group can take on. At this time it would remain as a working group and not a CoP. | Approved
#4 | Framework WG recommendation for the Joint Councils to sunset the PSSDC's Channel Shifting Working Group and the Joint Councils' Service Mapping Sub-Committee. | Approved
#5 | Framework WG recommendation that the three priorities of the Joint Councils - Digital Identity, Digital Strategy and Client Centric Services - be formalized into Working Groups (Co-Chaired by the current leads) and that a formal call for participation should be issued to the Joint Councils to help advance the work. | Approved
#6 | Framework Working Group recommendation on group structure related to what is a committee or working group versus community of practice. Members were in agreement for this criteria to be used when approving future groups of the Councils. | Approved
#7 | Framework WG recommendation that each group of the Councils (JC, PSSDC or PSCIOC) should have a defined 1. Terms of Reference, 2. Work plan approved by the Councils (Council the group report to) on a bi-annual basis, 3. regularly scheduled meetings, and 4. At least 1 co-chair being a member of the Councils. | Approved
#8 | Digital Strategy: Joint Councils members approved to use the TBS's Digital Principles to guide the work of the Councils and of all working groups and committees. Digital Strategy leads to take the lead on this work and to continue to work with Joint Councils in defining role related to pan-Canadian digital strategy. | Approved
JOINT COUNCILS TELECONFERENCE OF JUNE 7, 2018
#1 | Joint Councils’ members approved in principle the funding request by the Research Committee. ICCS to follow up by email on this matter. Members to advise if they have any questions or concerns related to this request. | Approved
JOINT COUNCILS TELECONFERENCE OF JULY 30, 2018
#1 | Joint Councils Members agreed to operationalize the work of the Framework Working Group and its recommendations related to: o Transfer of functions of the FWG to Joint Councils Co-Chairs, Priority leads and the ICCS, o funding request for one year contract position of up to $90K, o Sunset the work of the FWG. | Approved
#2 | Members agreed for the creation of the General Data Protection Regulation (GDPR) as a sub-group of the Privacy Sub-Committee. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html