## Action Items
| JOINT COUNCILS ACTION ITEMS |  |  |  | Last updated: Feb 14, 2023
|  | Next Joint Councils Meeting: | Feb 23rd 2023
| ACTION ITEM | LEADS | ASSIGNED | STATUS | NOTES
Joint Councils Meeting of January 19, 2023
#1B | Open Source Working Group Co-Chairs to explore the delivery of learning workshops and report back to the members at a future meeting on scope and funding required. | Open Source WG Chairs | 2023-01-19 | Pending | Update at an upcoming meeting
#2 | The Research Committee can support the Councils by establishing a research workplan based on the main priorities of the Councils. The Committee to table this workplan at an upcoming meeting. | Research Committee Chairs | 2023-01-19 | Pending | Research Committee to report back to Joint Councils
Joint Councils Meeting of November 4, 2022
#1D | The Canada Open Government CoP to report back to the Councils on the scope of work for the three proposed projects and funding request at an upcoming meeting. 1. User Centred Open Data Portals 2. Strengthening Public Engagement 3. Enhancing Engagement with the International Open Government Community | Canada Open Government WG | 2022-11-04 | Pending | Funding proposal to be tabled at an upcoming meeting.
Joint Councils Meeting of September 22, 2022
#1 | ICCS to connect with Code for Canada to explore other opportunities for collaboration with the Joint Councils. | ICCS and Code for Canada | 2022-09-22 | Pending | ICCS Secretariat to work with JC co/chairs re agenda.
#4A | Service to Business Working Group Co-Chairs to work with Digital Trust Program Executive team to align and support work related to digital credentials across jurisdictions with the work of digital identity. | Service to Business WG co-chairs | 2022-09-22 | Pending | S2B WG Chairs and Digital Trust Program Executive to discuss further.
#6B | ICCS Board to proceed with next steps on convening a task team to review the relationship between the ICCS and the Councils. | ICCS Board / Secretariat | 2022-09-22 | Underway | ICCS Board executives to work on next steps.
Joint Councils Meeting of June 28, 2022
#1 | Data Driven Intelligence Working Group to table research deliverable to the Councils for review and approval. | DDI WG | Jun-28-22 | Pending | DDI WG to provide an update on this work at the April 2023 meeting
Joint Councils Meeting of February 15, 2022
#2 | ICCS Secretariat to consult with the JC Co-Chairs on specific topic/theme for a potential workshop or activity led by Policy Horizons Canada. ICCS to coordinate future engagement and participation with Policy Horizons Canada. | ICCS | 2022-02-15 | Pending | potential item for upcoming meeting
Joint Councils Meeting of January 13, 2021
#2 | Digital ID Program Executive requested to work together with JEDIs to develop a standard approach with key principles and messaging for jurisdictions to use when dealing with vendors. Digital ID Program Executive to report back to the Joint Councils members on this item. | Digital ID Program Executive | 2021-01-13 | Pending | Peter Watkins to report on this item at a future JC meeting.

## Decisions
DECISIONS
| ITEM | STATUS
JOINT COUNCILS MEETING OF SEPTEMBER 22, 2022
#1 | Record of Decision of the Joint Councils’ meeting of February 15, 2022, approved without changes. | Approved
#2 | Agenda of September 28th, 2022, Joint Councils’ meeting approved without changes. | Approved
#3 | Members provided their support, in principle for the creation of a Digital Trust Program Office: A. Three components 1. FPT Secretariat and Communications. 2. Support for aligned collaboration of Jurisdictional Implementation Teams. 3. Preliminary support for the small and medium size jurisdictions. B. The elements of each component. C. The required funding levels for each component. | Approved
#4 | Members approved the 3 recommendations by the ICCS Board: 1. PSSDC and PSCIOC Support Services Fees for the 2022-2023 fiscal year be adjusted by a minimum 5%. 2. Effective 2023-24, the PSSDC and PSCIOC Support Services Fees will be indexed annually based on the Consumer Price Index (CPI). 3. Establish an ICCS-Councils Task Team to review the relationship between the ICCS and the Councils and determine what future services and support will be required, and what funding model(s) should be considered. | Approved
JOINT COUNCILS MEETING OF JUNE 28, 2022
#1 | Joint Councils members endorsed the scope of work of the Data Driven Intelligence WG and approval of $70,000 in funding for additional research. | Approved
#2 | Joint Councils members endorsed the proposal of the Analytics Playbook SG and approval of $15,000 in funding for the 2022 playbook refresh. | Approved
#3 | Joint Councils members endorsed the proposal of the Analytics Playbook SG and approval of $15,000 in funding for the 2022 playbook refresh. | Approved
JOINT COUNCILS MEETING OF OCTOBER 26, 2021
#1 | Record of Decision of the Joint Councils’ meeting of February 23, 2021 approved without changes | Approved
#2 | Agenda of October 26th, 2021 Joint Councils’ meeting approved without changes. | Approved
JOINT COUNCILS MEETING OF AUGUST 24, 2021
#1 | Joint Councils members approved the decision to: •officially sunset the Client Centric Services WG as all deliverables have been completed. •Client Centric Services Design and Community of Practice to provide oversight of the Interjurisdictional Citizen Centric Maturity Model Tool hosted on the ICCS website. | Approved
#2 | Joint Councils members approved to rescheduling the September meetings to October, due to the federal election and the impact this has on federal participation at the meetings. | Approved
#3 | Joint Councils members approved the creation of the CDO Community of Practice with the funding of $25,000 for a resource to provide secretarial support services for a one year period. | Approved
JOINT COUNCILS MEETING OF JUNE 28, 2021
#1 | Joint Councils’ members approved the funding of $22K for the annual refresh of the Analytics Playbook. | Approved
JOINT COUNCILS MEETING OF MAY 28, 2021
#1 | Joint Councils members endorsed the Terms of Reference of the Client Centric Services Design/Experience Community of Practice (CCSDE CoP) | Approved
JOINT COUNCILS MEETING OF MARCH 30, 2021
#1 | Joint Councils members approved the refreshed Terms of Reference of the Death Notification Community of Practice (formerly a working group). | Approved
JOINT COUNCILS MEETING OF FEBRUARY 23, 2021
#1 | Record of Decision of September 22nd, 2020 Joint Councils’ virtual meeting approved without changes | Approved
#2 | Agenda of February 23rd, 2021 meeting approved without changes. | Approved
#3 | Joint Councils members approved the decision to sunset the Client Centric Services Working Group after the completion of the Maturity Model Digital User Guide and Tools. | Approved
JOINT COUNCILS MEETING OF JANUARY 13, 2021
#1 | Joint Councils members approved the Data Driven Intelligence WG SoW with suggested changes required by members. | Approved
#2 | Open Source Working Group Terms of Reference and Workplan have been approved by Joint Councils members. | Approved
JOINT COUNCILS MEETING OF DECEMBER 11, 2020
#1 | Joint Councils Members approved the S2B mandate and proposed workplan. | Approved
JOINT COUNCILS MEETING OF NOVEMBER 26, 2020
#1 | Digital ID Program: Joint Councils members approved the recommendation for accelerating implementation of Pan-Canadian Digital ID by: 1. Forming an ADM level panel for the accelerated implementation of Pan-Canadian Digital Identity/Trust and 2. Comprised of ADM levels from organizations that state their intention to be an early implementor. | Approved
JOINT COUNCILS MEETING OF OCTOBER 29, 2020
#1 | Joint Councils members approved the recommendation for JEDIs to be the leaders representing their jurisdictions on all matters related to Digital ID. All other digital ID groups of the Councils, such as the IMSC and other sub-groups, to be sunset as their deliverables have been completed. | Approved
JOINT COUNCILS TELECONF OF JULY 22, 2020
#1 | Members approved the funding of $60,000 per year for three-years for the Research Analyst to produce the Research Committee deliverables and to provide strategic analysis support services to the Joint Councils. | Approved
#2 | Members approved having the Learning Event split in several sessions during the months of October to December. | Approved
JOINT COUNCILS MTG OF FEBRUARY 2020
#1 | Record of Decision of September 25th, 2019 Joint Councils’ meeting in Winnipeg approved without changes. | Approved
#2 | Agenda of February 26th and 27th, 2020 meeting approved without changes. | Approved
#3 | Joint Council’s members approved the decision to sunset the Digital Strategy Working Group. | Approved
#4 | Joint Council’s members approved the two priorities: Digital ID and Client Centric Services. | Approved
#5 | Joint Council’s members approved the funding of $100K for the Digital ID Program Director, plus $25K for the workshop. The funding for Digital ID representative’s travel for the workshop is to be funded by each jurisdiction, and if there’s budgetary constraints within the province, the Joint Councils will make an exception and provide funding to those who need travel assistance. | Approved
#6 | PSSDC and PSCIOC members approved in their separate meetings to move the Data Driven Intelligence Working Group under the Joint Council. | Approved
JOINT COUNCILS TELECONF OF JANUARY 16, 2020
#1 | Joint Councils approved an amount of up to $18K (exclusive of HST) for supplementary funding to the Client Centric Services Working Group for the development of an interactive tool. | Approved
JOINT COUNCILS CO-CHAIRS MEETING OF DECEMBER 10, 2019
#1 | Joint Councils meetings in February to start with individual Council meeting the morning of Feb 26th and have a 1.5 days Joint Councils meeting on Feb 26th and 27th, 2020. | Approved
#2 | Co-Chairs agreed to have an annual Co-Chairs strategic session. There is planning to meet again in June 2020 to continue this work. | Approved
JOINT COUNCILS MEETING OF SEPTEMBER 25, 2019
#1 | Record of Decision of February 27th, 2019 Joint Councils’ meeting in Ottawa approved without changes. | Approved
#2 | Agenda of September 25th, 2019 meeting approved without changes | Approved
#3 | Joint Councils’ Members approved tasking the Digital Strategy Working Group with oversight of the work related to the future strategic direction of the Councils. | Approved
#4 | Joint Councils’ members approved in principle to be flexible around the proposed new format for the meetings - Joint Councils 1½ day and ½ day for PSSDC and PSCIOC meetings - however only if this is required. | Approved
#5 | Joint Councils members approved Natasha Clarke as the new provincial co-chair of the Digital Strategy Working Group replacing Mark Burns. | Approved
#6 | Joint Councils members approved Sonya Read as the new Federal Co-Chair of the Data Driven Intelligence Working Group. | Approved
JOINT COUNCILS TELECONFERENCE OF AUGUST 14, 2019
#1 | Joint Council’s members approved the request of additional funding from the Digital Identity Group in the amount of $4,600 to complete the work led by consultant. | Approved
JOINT COUNCILS TELECONFERENCE OF APRIL 15, 2019
#1 | Joint Councils members approved funding of $20K for the CCS Working Group to hire a resource to work on testing the maturity model and developing a user guide on seniors’ service experience during and after a wildfire. | Approved
#2 | Joint Councils Members approved TBS as Co-Lead of the Digital Identity Priority Stream. | Approved
#3 | Members approved up to a maximum of $30K for the hiring of a resource to develop the governance piece. This amount will be split 50/50 between the Councils. ICCS to provide contract management support. | Approved
JOINT COUNCILS MEETING OF FEBRUARY, 2019
#3 | The Policy Paper has been endorsed by Joint Councils members. | Approved
#4 | Joint Councils Members approved the formation of an Interim Digital Identity Priority group. | Approved
#5 | Joint Councils Members approved funding, of up to $15K, for the hiring of a resource for work-related to the development of a governance framework (recommendations), including assisting the leads with the presentation for the Clerks and Cabinet Secretaries meeting in July 2019. | Approved
#6 | Joint Councils members approved the change to the Death Notification Working Group Terms of Reference to have a representative from Vital Stats as a third co-chair on the working group. | Approved
#7 | Joint Councils members approved the hiring of a Project Manager to help the Death Notification Working Group Co-Chairs to stay focus and deliver on this work. The Working Group would report back on required funding and scope of work. | Approved
JOINT COUNCILS TELECONFERENCE OF OCTOBER 29, 2018
#1 | Joint Councils Members approved the Client Centric Services Working Group Maturity Model, Terms of Reference and Work Plan. | Approved
#2 | Joint Councils Members approved the Privacy Sub-Committee’s Terms of Reference and Work Plan. | Approved
JOINT COUNCILS MEETING OF SEPTEMBER 26, 2018 (WHITEHORSE)
#1 | Joint Councils approved the decision for the CDI group to be moved under the IMSC. | Approved
#2 | Joint Councils approved the motion for the work of the Public Policy Working Group to continue. | Approved
#3 | Members agreed for Manitoba to host the September 2019 in-person meetings. | Approved
JOINT COUNCILS TELECONFERENCE OF JULY 30, 2018
#1 | Joint Councils Members agreed to operationalize the work of the Framework Working Group and its recommendations related to: 1. Transfer of functions of the FWG to Joint Councils Co-Chairs, Priority leads and the ICCS, 2. funding request for one year contract position of up to $90K, and 3. Sunset the work of the FWG. | Approved
#2 | Members agreed for the creation of the General Data Protection Regulation (GDPR) as a sub-group of the Privacy Sub-Committee. | Approved
JOINT COUNCILS TELECONFERENCE OF JUNE 7, 2018
#1 | Joint Councils’ members approved in principle the funding request by the Research Committee. ICCS to follow up by email on this matter. Members to advise if they have any questions or concerns related to this request. | Approved
JOINT COUNCILS MEETING OF FEBRUARY 21, 2018
#1 | Framework WG recommendation for the following groups to continue their work - PSSDC's Service Network Collaboration WG, Service to Business CoP, the Joint Councils' Canada's Open Gov WG, IMSC, CDI, DNWG, and the PSCIOC's Cloud WG. Members approved the FWG recommendation. | Approved
#2 | Framework WG recommendation for the work of the PSCIOC's NCSIP and the Joint Councils' Privacy Sub-Cmte and Research Committee to continue and for the Councils to leverage their expertise to advance the JC priorities. | Approved
#3 | Framework WG recommendation to task the PSCIOC's IT Procurement WG with activities related to priorities or transition to CoP: Kathryn Bulko, IT Procurement Chair, welcome suggestions from members on activities that this working group can take on. At this time it would remain as a working group and not a CoP. | Approved
#4 | Framework WG recommendation for the Joint Councils to sunset the PSSDC's Channel Shifting Working Group and the Joint Councils' Service Mapping Sub-Committee. | Approved
#5 | Framework WG recommendation that the three priorities of the Joint Councils - Digital Identity, Digital Strategy and Client Centric Services - be formalized into Working Groups (Co-Chaired by the current leads) and that a formal call for participation should be issued to the Joint Councils to help advance the work. | Approved
#6 | Framework Working Group recommendation on group structure related to what is a committee or working group versus community of practice. Members were in agreement for this criteria to be used when approving future groups of the Councils. | Approved
#7 | Framework WG recommendation that each group of the Councils (JC, PSSDC or PSCIOC) should have a defined 1. Terms of Reference, 2. Work plan approved by the Councils (Council the group report to) on a bi-annual basis, 3. regularly scheduled meetings, and 4. At least 1 co-chair being a member of the Councils. | Approved
#8 | Digital Strategy: Joint Councils members approved to use the TBS's Digital Principles to guide the work of the Councils and of all working groups and committees. Digital Strategy leads to take the lead on this work and to continue to work with Joint Councils in defining role related to pan-Canadian digital strategy. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html