## Action Items
| JOINT COUNCILS ACTION ITEMS |  |  |  | Last updated: Aug 30, 2019
|  | Next Joint Councils Meeting: | Wednesday, Sept. 25th, Winnipeg
| ACTION ITEM | LEADS | ASSIGNED | STATUS | NOTES
Joint Councils Teleconference of August 14, 2019
#1 | The ICCS, in collaboration with federal PSCIOC Co-Chair, to follow up with CIO Strategy Council to ensure that the discussion in September takes into consideration members’ feedback. | ICCS | 2019-08-14 | Completed | ICCS, in collaboration with PSCIOC and PSSDC federal co-chairs, followed up with CIOSC.
Joint Councils Teleconference of June 26, 2019
Digital Identity Priority Stream
#1C | Digital Identity Priority Stream Co-leads to report back on the Governance piece at the September Joint Council’s meeting. | Digital ID Co-Leads | 2019-06-26 | Underway | Update on the September 25th JC meeting agenda
#1E | Tim Bouma to report back on future developments of the PCTF at the Joint Councils meeting in September. | Digital ID Co-Leads | 2019-06-26 | Underway | Update on the September 25th JC meeting agenda
General Data Protection Regulation Working Group (under Privacy Sub-Committee)
#2A | GDPR Working Group to report back on the use cases that they are developing at the Joint Councils September meeting. Meeting. | GDPR Co-Chairs | 2019-06-26 | Pending | Update at an upcoming fall JC teleconference
#2B | Joint Councils members to send their feedback on the Terms of Reference and/or workplan to the GDPR Working Group’s Co-Chairs. | GDPR Co-Chairs | 2019-06-26 | Pending | Update at an upcoming fall JC teleconference
Death Notification Working Group
#3B | Death Notification Working Group to report back on their work at an upcoming fall teleconference. | DNWG Co-Chairs | 2019-06-26 | Pending | Update at the November 20th teleconference
Client Centric Services Working Group
#4 | Client Centric Services Working Group to report back on the testing of the Maturity Model at the September Joint Councils’ meeting. | CCS Co-Chairs | 2019-06-26 | Pending | Update at the November 20th teleconference
Joint Council's Strategic Policy Analyst
#5 | The Joint Councils Strategic Policy Analyst to report back on her work at the September Joint Councils’ meeting. | JC Strategic Policy Analyst | 2019-06-26 | Underway | Update on the September 25th JC meeting agenda
Joint Councils Teleconference of April 15, 2019
Research Committee
#2C | Research Committee Co-Chairs to report back to Joint Councils on next steps related to funding request for hiring of resource to continue the work of the committee. | Research Committee Co-Chairs | 2019-04-15 | Underway | Joint Councils Co-Chairs approved a one year contract for a JC Research Analyst. Update at the November 20th JC teleconference.
Joint Councils Strategic Policy Analyst
#4 | ICCS to send an e-mail seeking member feedback on the Strategic Policy Analyst’s presentation (proposed definitions for short term goals and guidelines for formation of new working groups). Approval to be sought at an upcoming teleconference. | JC Strategic Policy Analyst | 2019-04-15 | Pending | Cathy Kealey to seek approval on this item at the September meeting (as part of a strategic discussion)
Joint Councils In-Person Meeting of February 27, 2019
Digital Identity Priority Stream
#1A | Digital Identity Leads to update Joint Councils regarding the Declaration on Digital Identity (re: all signatures) at the next in-person meeting in Winnipeg, in September 2019. | Digital ID Co-Leads | 2019-02-27 | Underway | Pending signatures (2) to be done at the September meeting in Winnipeg.
#1F | ISED to provide updates on the Digital Identity for Business, verified organization at an upcoming Joint Councils meeting. | ISED | 2019-02-27 | Underway | Item on the September 25th meeting agenda
Death Notification Working Group
#2 | Joint Councils members approved the hiring of a Project Manager to help the Death Notification Working Group Co-Chairs to stay focus and deliver on this work. The Death Notification Working Group Co-Chairs to report back on required funding and scope of work at an upcoming teleconference. Death Notification Working Group to provide updated Terms of Reference at an upcoming meeting. | DNWG Co-Chairs | 2019-02-27 | Pending | DNWG to provide update at the Nov 20th JC teleconference following their late October in person workshop.
Digital Strategy Working Group
#4A | Digital Strategy Working Group Co-Chairs to do an assessment on where Canadian jurisdictions are at in terms of Digital Strategy, identifying pain points (e.g. Accessibility and Inclusion) and share it with Joint Councils members. | Digital Strategy Co-Chairs | 2019-02-27 | Pending | Item on the September 25th meeting agenda
#4B | Digital Strategy Working Group Co-Chair to develop a scope of work for the working group and report back to the Joint Councils at an upcoming teleconference. | Digital Strategy Co-Chairs | 2019-02-27 | Pending | Item on the September 25th meeting agenda
Joint Councils Meeting of September 26, 2018 (Whitehorse)
Jurisdictional Item
#3 | BC to report on the evolution of the Verifiable Organization Network (VON) at a future Joint Councils meeting. | British Columbia | 2018-09-26 | Pending | Item to be scheduled at an upcoming JC teleconference/meeting agenda
Research Committee
#4 | Joint Councils Research Committee requested to review and unpack the results of Citizens First 8 and provide recommendations to the Councils on areas of focus to have strategic conversation on the results. | Research Committee Co-Chairs | 2018-09-26 | Pending | Item to be scheduled at an upcoming JC teleconference/meeting agenda
Joint Councils Teleconference of July 30, 2018
Framework Working Group
#1A & #1C | Framework Working Group Co-Chairs to work with ICCS to procure the services of a resource and manage one-year contract. Natasha Clarke and Sophia Howse to provide a report to members in fall 2019 regarding the contract position to assess whether or not this has achieved its objectives. | FWG Leads and ICCS Secretariat | 2018-07-30 | Pending | One year contract position from Dec. 3rd 2018 to Dec. 2nd 2019. Update in Fall 2019.
Joint Councils Meeting of February 21, 2018 (Toronto)
Framework Working Group
#1E (ii) | Framework Working Group to develop governance structure (dashboard) of all working groups of the Councils. | FWG Leads and ICCS Secretariat | 2018-02-21 | Pending | Item for discussion following September 2019 meeting
#1F
Joint Councils Meeting of February 22, 2017
| Framework Working Group to work on development of a Joint Councils’ Terms of Reference (currently there is only a mandate for PSSDC and PSCIOC) and recommendations on the future of the FWG and accountability of the Councils to the logic model. FWG to provide an update at an upcoming teleconference and/or meeting. | FWG Leads and ICCS Secretariat | 2017-02-22 | Pending | Item for discussion following September 2019 meeting

## Decisions
DECISIONS
| ITEM | STATUS
JOINT COUNCILS TELECONFERENCE OF AUGUST 14, 2019
#1 | Joint Council’s members approved the request of additional funding from the Digital Identity Group in the amount of $4,600 to complete the work led by consultant. | Approved
JOINT COUNCILS TELECONFERENCE OF APRIL 15, 2019
#1 | Joint Councils members approved funding of $20K for the CCS Working Group to hire a resource to work on testing the maturity model and developing a user guide on seniors’ service experience during and after a wildfire. | Approved
#2 | Joint Councils Members approved TBS as Co-Lead of the Digital Identity Priority Stream. | Approved
#3 | Members approved up to a maximum of $30K for the hiring of a resource to develop the governance piece. This amount will be split 50/50 between the Councils. ICCS to provide contract management support. | Approved
JOINT COUNCILS MEETING OF FEBRUARY, 2019
#1 | Record of Decision of September 26th, 2018 Joint Councils’ meeting in Whitehorse has been approved without changes. | Approved
#2 | Agenda of February 27th, 2019 meeting has been approved without changes. | Approved
#3 | The Policy Paper has been endorsed by Joint Councils members. | Approved
#4 | Joint Councils Members approved the formation of an Interim Digital Identity Priority group. | Approved
#5 | Joint Councils Members approved funding, of up to $15K, for the hiring of a resource for work-related to the development of a governance framework (recommendations), including assisting the leads with the presentation for the Clerks and Cabinet Secretaries meeting in July 2019. | Approved
#6 | Joint Councils members approved the change to the Death Notification Working Group Terms of Reference to have a representative from Vital Stats as a third co-chair on the working group. | Approved
#7 | Joint Councils members approved the hiring of a Project Manager to help the Death Notification Working Group Co-Chairs to stay focus and deliver on this work. The Working Group would report back on required funding and scope of work. | Approved
JOINT COUNCILS TELECONFERENCE OF OCTOBER 29, 2018
#1 | Joint Councils Members approved the Client Centric Services Working Group Maturity Model, Terms of Reference and Work Plan. | Approved
#2 | Joint Councils Members approved the Privacy Sub-Committee’s Terms of Reference and Work Plan. | Approved
JOINT COUNCILS MEETING OF SEPTEMBER 26, 2018 (WHITEHORSE)
#1 | Joint Councils approved the decision for the CDI group to be moved under the IMSC. | Approved
#2 | Joint Councils approved the motion for the work of the Public Policy Working Group to continue. | Approved
#3 | Members agreed for Manitoba to host the September 2019 in-person meetings. | Approved
JOINT COUNCILS TELECONFERENCE OF JULY 30, 2018
#1 | Joint Councils Members agreed to operationalize the work of the Framework Working Group and its recommendations related to: 1. Transfer of functions of the FWG to Joint Councils Co-Chairs, Priority leads and the ICCS, 2. funding request for one year contract position of up to $90K, and 3. Sunset the work of the FWG. | Approved
#2 | Members agreed for the creation of the General Data Protection Regulation (GDPR) as a sub-group of the Privacy Sub-Committee. | Approved
JOINT COUNCILS TELECONFERENCE OF JUNE 7, 2018
#1 | Joint Councils’ members approved in principle the funding request by the Research Committee. ICCS to follow up by email on this matter. Members to advise if they have any questions or concerns related to this request. | Approved
JOINT COUNCILS MEETING OF FEBRUARY 21, 2018
#1 | Framework WG recommendation for the following groups to continue their work - PSSDC's Service Network Collaboration WG, Service to Business CoP, the Joint Councils' Canada's Open Gov WG, IMSC, CDI, DNWG, and the PSCIOC's Cloud WG. Members approved the FWG recommendation. | Approved
#2 | Framework WG recommendation for the work of the PSCIOC's NCSIP and the Joint Councils' Privacy Sub-Cmte and Research Committee to continue and for the Councils to leverage their expertise to advance the JC priorities. | Approved
#3 | Framework WG recommendation to task the PSCIOC's IT Procurement WG with activities related to priorities or transition to CoP: Kathryn Bulko, IT Procurement Chair, welcome suggestions from members on activities that this working group can take on. At this time it would remain as a working group and not a CoP. | Approved
#4 | Framework WG recommendation for the Joint Councils to sunset the PSSDC's Channel Shifting Working Group and the Joint Councils' Service Mapping Sub-Committee. | Approved
#5 | Framework WG recommendation that the three priorities of the Joint Councils - Digital Identity, Digital Strategy and Client Centric Services - be formalized into Working Groups (Co-Chaired by the current leads) and that a formal call for participation should be issued to the Joint Councils to help advance the work. | Approved
#6 | Framework Working Group recommendation on group structure related to what is a committee or working group versus community of practice. Members were in agreement for this criteria to be used when approving future groups of the Councils. | Approved
#7 | Framework WG recommendation that each group of the Councils (JC, PSSDC or PSCIOC) should have a defined 1. Terms of Reference, 2. Work plan approved by the Councils (Council the group report to) on a bi-annual basis, 3. regularly scheduled meetings, and 4. At least 1 co-chair being a member of the Councils. | Approved
#8 | Digital Strategy: Joint Councils members approved to use the TBS's Digital Principles to guide the work of the Councils and of all working groups and committees. Digital Strategy leads to take the lead on this work and to continue to work with Joint Councils in defining role related to pan-Canadian digital strategy. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html