## Action Items
| JOINT COUNCILS ACTION ITEMS |  |  |  | Last updated: February 5, 2019
|  | Next Joint Councils Meeting: | Wednesday, Feb 27th, 2019
| ACTION ITEM | LEADS | ASSIGNED | STATUS | NOTES
Joint Councils Teleconference of December 14, 2018
Digital Strategy Working Group
#1A | Digital Strategy Working Group Co-Chairs to work with the Joint Councils Strategic Policy Analyst to design the Digital Strategy item for the Ottawa Joint Councils meeting. | Guy Gordon, Mark Burns, Sean McLeish, and Cathy Kealey | 2018-12-14 | Underway | Agenda item under development
#1B | Digital Strategy item to be included in the Joint Councils Ottawa meeting agenda. | Digital Strategy Working Group Co-Chairs and ICCS Secretariat | 2018-12-14 | Underway | Item on the February 27th Joint Councils Agenda
Digital Identity Priority Stream
#2A | Digital Identity Priority Stream Co-Leads to make the amendments on the Digital Identity Declaration and circulate version 1, via ICCS, to members who are ready to sign. | Jackie Stankey, Sophia Howse & ICCS | 2018-12-14 | Underway | Item on the February 27th Joint Councils Agenda
#2B | A version 2 of the Digital Identity Declaration to be circulated within 3 months to obtain remaining signatures (for those members unable to sign at this time). | Jackie Stankey, Sophia Howse & ICCS | 2018-12-14 | Pending
Joint Councils Teleconference of October 29, 2018
General Data Protection Regulation Working Group (under Privacy Sub-Committee)
#2A | GDPR Working Group Co-Chairs to share a copy of the GDPR 101 with Joint Councils members. | Keleigh Annau, Charles Taillefer | 2018-10-29 | Pending | Awaiting further information from GDPR Working Group
#2B | GDPR Working Group Co-Chairs to provide information on the GPDR’s extra territorial guidelines when it becomes available. | Keleigh Annau, Charles Taillefer | 2018-10-29 | Pending | Awaiting further information from GDPR Working Group
Joint Councils Meeting of September 26, 2018 (Whitehorse)
Digital Identity Priority Stream
#1B | Chantal Ritcey to share infographic and proposal for a communications toolkit with Joint Councils members at an upcoming teleconference. | Chantal Ritcey | 2018-09-26 | Pending | Update pending - upcoming meeting/teleconference
#1D | IMSC will present the beta version of Verified Person (Trust Framework) tested with several jurisdictions at the next Joint Councils meeting. | Marc Brouillard, Rob Devries, IMSC Co-Chairs | 2018-09-26 | Underway | Item on the February 2019 JC meeting agenda
#1E | ISED to provide a demo of the Verified Organization at the next Joint Councils meeting. | Vidya ShankarNarayan, PSSDC Member | 2018-09-26 | Underway | Item on the February 2019 JC meeting agenda
#1F | Joint Councils members to review the Public Policy Recommendations paper. Members to have a discussion on this paper to get endorsement of the 3 guiding principles by the next Joint Councils meeting. | PSCIOC and PSSDC Members | 2018-09-26 | Pending | Update on this item at the Dec 14th teleconference. Further discussion and endorsement at the next JC meeting in February 2019.
#1G | ICCS to discuss with the Joint Councils Co-Chairs invitation of the Vital Statistics group to participate in future Joint Councils meetings as an observer. | PSCIOC, PSSDC Co-Chairs, ICCS | 2018-09-26 | Underway | Death Notification Working Group to provide an update on this item at the Feb 27th meeting.
#1J | Digital Identity Priority Stream Co-Leads to report on the Roadmap at upcoming teleconference. | Jackie Stankey, Sophia Howse, Digital Identity Priority Stream Co-Leads | 2018-09-26 | Underway | Item on the February 2019 JC meeting agenda
Jurisdictional Item
#3 | BC to report on the evolution of the Verifiable Organization Network (VON) at a future Joint Councils meeting. | CJ Ritchie, Bev Dicks | 2018-09-26 | Pending | Item to be scheduled at an upcoming JC teleconference/meeting agenda
Research Committee
#4 | Joint Councils Research Committee requested to review and unpack the results of Citizens First 8 and provide recommendations to the Councils on areas of focus to have strategic conversation on the results. | Richard Dalpé, Guy Gordon, Research Committee Co-Chairs | 2018-09-26 | Pending | Update on April 15, 2019 teleconference
Joint Councils Teleconference of July 30, 2018
Framework Working Group
#1A & #1C | Framework Working Group Co-Chairs to work with ICCS to procure the services of a resource and manage one-year contract. Natasha Clarke and Sophia Howse to provide a report to members in fall 2019 regarding the contract position to assess whether or not this has achieved its objectives. | Natasha Clarke, Sophia Howse & ICCS | 2018-07-30 | Underway | One year contract position from Dec. 3rd 2018 to Dec. 2nd 2019.
General Data Protection Regulation Working Group (under Privacy Sub-Committee)
#2B | The GDPR Group to share their Terms of Reference and work plan with members at an upcoming meeting/teleconference. | Chad Hoskins | 2018-07-30 | Pending | Discussion on GDPR held on October 29th. Further update pending regarding ToR and work plan.
Joint Councils Teleconference of June 7, 2018
Research Committee
#1B | Research Committee Co-Chairs to provide progress report in fall of 2018 related to longer term funding and other work program elements. | Richard Dalpé, Guy Gordon | 2018-07-06 | Pending | Update on April 15, 2019 teleconference
Joint Councils Meeting of February 21, 2018 (Toronto)
Framework Working Group
#1E (i) | Framework Working Group to develop guideline or "cheat-sheet", for Councils' approval, to help ensure the proper type of group is created, when required. | FWG Leads and ICCS Secretariat | 2018-02-21 | Pending | Joint Councils Strategic Policy Analyst to report back on this item - Spring 2019 teleconference
#1E (ii) | Framework Working Group to develop governance structure (dashboard) of all working groups of the Councils. | FWG Leads and ICCS Secretariat | 2018-02-21 | Underway | Joint Councils Strategic Policy Analyst to report back on this item - Spring 2019 teleconference
Digital Strategy Working Group
#2A | Digital Strategy: Each jurisdiction to develop their own jurisdictional digital principles and to have this ready for the next in person meeting of September 26th. Members to have a collective review of all digital principles to check for alignment. | Guy Gordon, Mark Burns, Sean McLeish | 2018-02-21 | Pending | Waiting for further feedback on this item from the Digital Strategy working group. Discussion of the work of the Digital Strategy Working Group on the February JC agenda.
#2B | Digital Strategy: Joint Councils members approved to use the TBS's Digital Principles to guide the work of the Councils and of all working groups and committees. Digital Strategy leads to take the lead on this work and to continue to work with Joint Councils in defining role related to pan-Canadian digital strategy. | Guy Gordon, Mark Burns, Sean McLeish | 2018-02-21 | Pending | Waiting for further feedback on this item from the Digital Strategy working group. Discussion of the work of the Digital Strategy Working Group on the February JC agenda.
#1F | Joint Councils Meeting of February 22, 2017
Framework Working Group
| Framework Working Group to work on development of a Joint Councils’ Terms of Reference (currently there is only a mandate for PSSDC and PSCIOC) and recommendations on the future of the FWG and accountability of the Councils to the logic model. FWG to provide an update at an upcoming teleconference and/or meeting. | Natasha Clarke, Sophia Howse | 2017-02-22 | Pending | Joint Councils Strategic Policy Analyst to report back on this item - Spring 2019 teleconference