## Action Items
| PSSDC ACTION ITEMS |  |  |  | Last updated: 05/09/2018
|  | Next PSSDC Meeting: | Sept. 27th, 2018 Whitehorse, YT
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSSDC Teleconferences of June 4th and July 25th were cancelled by Co-Chairs.
PSSDC Teleconference of April, 19, 2018
#2B | Service Network Collaboration Working Group: SNC Co-Chairs to provide feedback from FPT DMs’ Table on Service Partnerships Playbook at the June PSSDC teleconference. | Rob Horwood, Annetter Vermaeten | 2018-04-19 | Underway | Item deferred to September meeting
#2C | Service Network Collaboration Working Group: Discussion on engagement strategy for the Service Partnerships Playbook to be scheduled at upcoming PSSDC teleconference. | Rob Horwood, Annetter Vermaeten | 2018-04-19 | Underway | Item deferred to September meeting
#3 | Service to Business (S2B) Community of Practice: Final version of BN Playbook to be presented at the June PSSDC teleconference. | Anne Matthews, Natalie McGee | 2018-04-19 | Underway | Item deferred to September meeting
#4 | Data Driven Intelligence: Progress report on DDI to be scheduled at an upcoming PSSDC teleconference. | Guy Gordon | 2018-04-19 | Underway | Item on the September meeting agenda
PSSDC Meeting of February 22, 2018 (Toronto)
#2B | Service Network Collaboration Working Group: SNC Co-chairs to draft an engagement strategy for the Partnerships Guide and share with PSSDC members for review. | Annette Vermaeten, Rob Horwood | 2018-02-22 | Underway | Item on September meeting agenda
#2D | Service Network Collaboration Working Group Co-Chairs to continue the work on Geo-mapping: Internal tool: Internal points of service mapping tool be updated while searching for long term solution. Jurisdictions to be engaged to implement more formal and automated processes for updates. More communication and outreach planned with jurisdictions and federal partners to put the tool in the hands of users. Public Facing Tool: Co-chairs to develop a process to seek client views on client's main pain points before developing a solution. | Annette Vermaeten, Rob Horwood | 2018-02-22 | Underway | Item on September meeting agenda
#3C | Service to Business (S2B) Community of Practice Co-Chairs to consider developing a document with concrete things that the PSSDC can focus on re: EBS. Suggestion to convene a focus group with members to identify what the challenges are, progress/successes to date and what next for the update to Clerks. | Anne Matthews, Chris Laverdure | 2018-02-22 | Underway | Update on April 19th, further follow up at an upcoming PSSDC teleconference (fall 2018)
#4B | Data Driven Intelligence: PSSDC members requested DDI Leads to develop a Terms of Reference and work plan for the DDI priority. Terms of Reference and work plan to be formalized at an upcoming PSSDC teleconference/meeting. | Guy Gordon | 2018-02-22 | Underway | Item on the September meeting agenda
$4C | Ron Hinshaw, BC, offered to do a demo to PSSDC on BC pilot related to Open Source. (BC is currently developing tool) | Ron Hinshaw | 2018-02-22 | Pending | Item scheduled in fall 2018.
#4D | Data Driven Intelligence: Continue to develop and enhance a pan-Canadian E-vulnerability Index and explore a Playbook. Update to be provided to PSSDC at an upcoming meeting | Guy Gordon | 2018-02-22 | Underway | Item on the September meeting agenda

## Decisions
DECISIONS
| ITEM | STATUS
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC P/T Co-Chair's position: PSSDC members approved a one year extension of the P/T Co-Chair's (Natasha Clarke) position from Sept. 2018 to Sept. 2019. The P/T Co-Chair position would end at the Sept. 2019 PSSDC meeting. | Approved
#2 | Data Driven Intelligence: PSSDC members adopted a recommendation for DDI to become a priority of the PSSDC. | Approved
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC members approved in principle the Service Network Collaboration's Service Partnerships Playbook. | Approved in principle

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html