## Action Items
| PSCIOC ACTION ITEMS |  |  |  | 2018-05-09
|  | Next PSCIOC Meeting: | September 27, 2018 Whitehorse, YT
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSCIOC Teleconference of July 23, 2018
#1 | Information and Communication Technology (ICT) Policy Working Group - Framework Working Group recommended for the ICT Policy Working Group to transition to a Community of Practice. PSCIOC members agreed to reach out to ICT Policy Working Group Co-Chairs and get a better understanding of their current work and identify areas of potential collaboration and support in order to determine next steps. PSCIOC members had a discussion on July 23rd on this matter. The ICT Policy WG Co-chairs requested to report back with recommendations on work for this group at an upcoming teleconference. | Keith Douglass, Co-Chair | 2018-07-23 | Pending | Item on the November 8th teleconference agenda
#2 | Sandra Cascadden requested for a further conversation on FOI requests to be added to the September meeting agenda. | Sandra Cascadden | 2018-07-23 | Underway | Item on September meeting agenda
PSCIOC Teleconference of June 20, 2018
#1 | Cloud Working Group Co-Chairs to present the results of the Cloud Benefit Realization Survey at the next PSCIOC in-person meeting (September 27th). | Denise Gomes, Stephen Gordon | 2018-06-20 | Underway | Item on September meeting agenda
#2 | Microsoft invitation: Discussion on shaping an invitation for Microsoft to present at the February 2019 meeting in Ottawa to be included in PSCIOC September meeting agenda. | PSCIOC Co-Chairs / Members | 2018-06-20 | Pending | Item on September meeting agenda
PSCIOC Teleconference of April 20, 2018
#2A | DIACC to be invited to provide an update report on their current work. | ICCS Secretariat | 2018-04-20 | Pending | DIACC to present to the JC at an upcoming meeting/teleconference
PSCIOC Meeting of February 22, 2018 (Toronto)
#1A | NCSIP to keep up to date the following matrix: Cyber Security Services Capabilities, Jurisidictions Supported Stakeholders and Cyber Security Artifacts Availability. NCSIP to report back to PSCIOC on changes to these matrices and for further discussion at an upcoming teleconference/meeting. | Martin Dinel, NCSIP Chair | 2018-02-22 | Ongoing | Item on September meeting agenda
#1B | NCSIP to report back to PSCIOC on how the government can assist in encouraging schools to include cyber security as part of their curriculum. NCSIP plans to deliver the following paper at an upcoming teleconference/meeting: 1. Development of Skilled Cyber Security Resources (position of all jurisdictions CISOs regarding involvement of governments in post-secondary education programs to develop more cyber security talent and skilled resources) and 2. Cyber Security Awareness in K-12 System (NCSIP's position regarding involvement of the government in providing cyber threat and cyber security awareness training for K-12 students). | Martin Dinel, NCSIP Chair | 2018-02-22 | Underway | Item on September meeting agenda
#1C | NCSIP to keep ongoing tracking on the topic of Cyber Insurance and to report back to PSCIOC at a later date. | Martin Dinel, NCSIP Chair | 2018-02-22 | Pending | Update at an upcoming teleconference or meeting
#1D | NCSIP Chair suggested taking a closer look at recent NCSIP achievements as well as national cyber security requirements that may not currently be satisfied to potentially revise the committee’s terms of reference by Fall 2018 with the objective of improving Canada’s overall cyber security posture. NCSIP will report back with recommendations on this item in a few months (summer/fall 2018). | Martin Dinel, NCSIP Chair | 2018-02-22 | Pending | Item on September meeting agenda
#2 | Information Management (IM) Sub-Committee - Framework Working Group recommended for the IM Sub-Committee to transition to a Community of Practice. PSCIOC members agreed to keep group as is for now and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be tasked to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at an upcoming teleconference. | PSCIOC Co-Chairs/Members | 2018-02-22 | Pending | Item for discussion at an upcoming PSCIOC teleconference (Dec 19, 2018)
#3 | Information and Communication Technology (ICT) Policy Working Group - Framework Working Group recommended for the ICT Policy Working Group to transition to a Community of Practice. PSCIOC members agreed to reach out to ICT Policy Working Group Co-Chairs and get a better understanding of their current work and identify areas of potential collaboration and support in order to determine next steps. PSCIOC members to have a further discussion on this item at an upcoming teleconference. (i.e. VoIP, social media policy, procurement) | PSCIOC Co-Chairs/Members | 2018-02-22 | Completed | Item on the July 23 teleconference agenda
PSCIOC Teleconference of Nov. 20, 2017
#4 | Members were in agreement to pursue linkages/partnerships with the CIO Strategy Council. ICCS Secretariat to follow up with TBS (Alex Benay) around next steps in connecting the PSCIOC with the CIO Strategy Council and to provide an update to members. | Alex Benay, TBS | 2017-11-20 | Pending | Item for update at an upcoming teleconference (Nov tbc)
#7 | Members agreed to work on shaping the invitation to Microsoft for the February in person meeting. PSCIOC needs to have some email communication on how to shape the invitation and for members to review and provide feedback in order to confirm Microsoft’s participation. | PSCIOC Co-Chairs/Members | 2017-11-20 | Pending | Item for discussion at the September PSCIOC meeting (invitation for Feb 2019)
PSCIOC Meeting of October 5, 2017
#1D | New Brunswick (member) to provide information at the next meeting/teleconference on the Canadian Institute for Cyber Security located in New Brunswick (in response to how to integrate cyber security into the curriculum). | NB Member | 2017-10-05 | Pending | Update at an upcoming teleconference in fall 2018.

## Decisions
DECISIONS
| ITEM | STATUS
PSCIOC MEETING OF FEBRUARY 22, 2018
#1 | PSCIOC members approved the request by NCSIP to fund four day meetings twice a year, up to a maximum of 8 meeting days per year. (The current policy only allows up to a maximum of 6 meeting days per year.) This approval only applies to NCSIP and not to other groups of PSCIOC. | Approved
#2 | NCSIP: General agreement (access and support) in principle by members on all the recommendations by NCSIP. | Approved
#3 | Information Management (IM) Sub-Committee - Framework Working Group recommended for the IM Sub-Committee to transition to a Community of Practice. PSCIOC members agreed to keep group as is for now and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be tasked to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at an upcoming teleconference. | Approved
#4 | Information and Communication Technology Policy Working Group - Framework Working Group recommended for the ICT Policy Working Group to transition to a Community of Practice. PSCIOC members agreed to reach out to ICT Policy Working Group Co-Chairs and get a better understanding of their current work and identify areas of potential collaboration and support in order to determine next steps. PSCIOC members to have a further discussion on this item at an upcoming teleconference. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html