## Action Items
| PSCIOC ACTION ITEMS |  |  |  | Updated October 18, 2021
|  | Next PSCIOC meeting: | October 27th, 2021
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSCIOC Meeting of August 12, 2021
#1 | Donald Messier, PHAC, to share with the PSCIOC members the governance structure related to the proof of vaccination, and pilot opportunities at an upcoming meeting. (Action item from July 9th meeting: TBS/PHAC to report back at a future PSCIOC meeting on: a) Proposed plan to form a group with structured governance, mandate, secretariat support, funding model and also look to leverage the existing JEDI group structure to move this forward. b) Get a better understanding of what P/Ts need in terms of support to advance this. c) Health CIOs to be included as stakeholders in this group.) | FPT TCC | 2021-08-16 | Pending | Update at the November PSCIOC meeting.
PSCIOC Meeting of June 16, 2021
#2 | ICCS to connect with NCSIP Chair for future presentations / discussions related to cybersecurity topics and engaging Privacy Commissioners. | ICCS | 2021-06-23 | Underway | ICCS Secretariat working with NCSIP Chair on a presentation to PSCIOC on cybersecurity.
PSCIOC Meeting of April 28, 2021
#1A | PSCIOC members asked for clarity around the role and work of the CIO Strategy Councils as it relates to the Joint Councils’ Digital Identity Program. PSCIOC Co-Chairs to have discussion on this matter and report back to PSCIOC members at an upcoming meeting. | PSCIOC Co-Chairs | Apr-28-21 | Underway | Digital ID Program Executive to report back on this item at JC. Part of a previous ask tabled at JC.
PSCIOC Meeting of March 31, 2021
Cloud Working Group
#2A | The ICCS to work with the PSCIOC P/T Co-Chair and the Cloud WG Co-Chair offices to schedule the one-on-one meetings with the PSCIOC members to discuss the mandate of Cloud WG. | ICCS / PSCIOC P/T Chair | 2021-03-31 | Underway | Jurisdictional consultations are underway from June to September. Update at the December PSCIOC meeting.
PSCIOC Meeting of February 24, 2021
BC DevOps Lab
#1 | Hayden Lansdell, BC, to share with PSCIOC members at an upcoming meeting: • information on the technical skills of the open shift container platform that BC has or how they propagated greater code sharing across government • information on Call with Us and Sprint with Us procurement programs • the governance model changes related to the transition from waterfall to agile model. | PSCIOC Member British Columbia | 2021-02-24 | Underway | follow up presentation by BC at the November 24th meeting.
PSCIOC Meeting of November 5, 2020
#2A | ICCS to send out a jurisdictional scan to the PSCIOC members based on comments from members on the risk management artifacts and decision-making process. ICCS secretariat to consult with co-chairs on the curated approach to scan. The Research Analyst to analyze the results of the jurisdictional scan and share the report with the co-chairs to be part of the agenda for the upcoming meeting. | ICCS Secretariat | 2020-11-05 | Pending | Secretariat awaiting further direction from Chairs.
PSCIOC Meeting of October 22, 2020
#2 | Denis Skinner to report back at a future PSCIOC meeting on the federal government perspective related to Cabinet and Treasury Board memos - digital signature. | PSCIOC Co-Chair, TBS | 2020-10-22 | Pending | Update at an upcoming meeting.

## Decisions
DECISIONS
| ITEM | STATUS
PSCIOC MEETING OF May 19, 2021
#1 | PSCIOC members approved for Tracy Wood to serve an additional year as PSCIOC P/T Co-Chair, until June 1, 2022. | Approved
PSCIOC MEETING OF March 31, 2021
#1 | PSCIOC members approved the proposed IT Procurement CoP Terms of Reference | Approved
#1 | The P/T Co-Chair and Cloud WG Co-Chair to meet with PSCIOC members to discuss the mandate and future of the Cloud Working Group. | Approved
PSCIOC MEETING OF February 24, 2021
#1 | Record of Decision of September 23, 2020 PSCIOC meeting approved without changes. | Approved
#1 | Record of Decision of September 23, 2020 PSCIOC meeting approved without changes. | Approved
PSCIOC MEETING OF November 5 2020
#1 | PSCIOC members approved the ICT Community of Practice Terms of Reference. | Approved
PSCIOC MEETING OF JUNE 4 2020
#1 | PSCIOC Members agreed on moving from weekly PSCIOC meeting to bi-weekly meetings until further notice. | Approved
PSCIOC MEETING OF MAY 21 2020
#1 | PSCIOC Members approved Zelko Holjevac as the new Lead of the Microsoft Office 365 group. | Approved
PSCIOC MEETING OF APRIL 24 2020
#1 | PSCIOC members decided to invite the PSSDC members at their April 30th meeting to discuss the Business Resumption Planning. | Approved
PSCIOC MEETING OF MARCH 24, 2020
#1 | Members approved the decision of weekly PSCIOC meetings to discuss the work during the COVID-19 pandemic. | Approved
PSCIOC MEETING OF FEBRUARY 26, 2020
#1 | Record of Decision of September 26, 2019, PSCIOC meeting in Winnipeg approved without changes. | Approved
#2 | Agenda of February 26th, 2020 PSCIOC meeting approved. | Approved
#3 | CJ Ritchie moved that the Data Driven Intelligence (DDI) Group be moved to the Joint Councils; seconded Natasha Clarke. | Approved
#4 | Catherine Desgagnés-Belzil moved that the Service to Business Working Group be moved to the Joint Councils; seconded Natasha Clarke. | Approved
PSCIOC TELECONFERENCE OF JANUARY 17, 2020
#1 | PSCIOC members were in support of adopting recommendation #3 to adjust the PSCIOC annual contributions to a phased-in approach. Adjustment would take effect starting fiscal period 2020-2021. | Approved
PSCIOC MEETING OF SEPTEMBER 26, 2019 (WINNIPEG)
#1 | Record of Decision of February 28th, 2019, PSCIOC meeting in Ottawa approved without changes. | Approved
#2 | Agenda of September 26th, 2019 PSCIOC meeting approved. | Approved
PSCIOC TELECONFERENCE OF AUGUST8, 2019
#1 | Record of Decision from June 10 Teleconference were approved | Approved
#1 | PSCIOC Members confirmed Tracy Wood as the new PSCIOC Co-Chair, starting on June 1st, 2019. | Approved
#2 | PSCIOC Members confirmed Bonnie Schmidt as the new PSCIOC Treasurer starting in August 2019. | Approved
#3 | PSCIOC Members approved the Cloud Working Group Workplan and updated Terms of Reference with requested amendment. | Approved
PSCIOC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | As FPTM CIOs, we agree to go to our own jurisdiction and deal with the http issue (moving to https). Jurisdictions can use the federal tools available. Members to advise their jurisdiction that this was brought up by NCSIP and we need to take action to clean this up. NCSIP to track the inventories and progress as part of the artifacts they are collecting. | Approved
#2 | PSCIOC members agreed for MISA to be able to share information from the jurisdictional information sharing collected for each in person meeting, however confidential information (or what is considered sensitive information) can only be shared if the jurisdictional member (author) is consulted and approval is given to share. | Approved
PSCIOC MEETING OF FEBRUARY 22, 2018
#1 | PSCIOC members approved the request by NCSIP to fund four day meetings twice a year, up to a maximum of 8 meeting days per year. (The current policy only allows up to a maximum of 6 meeting days per year.) This approval only applies to NCSIP and not to other groups of PSCIOC. | Approved
#2 | NCSIP: General agreement (access and support) in principle by members on all the recommendations by NCSIP. | Approved
#3 | Information Management (IM) Sub-Committee - Framework Working Group recommended for the IM Sub-Committee to transition to a Community of Practice. PSCIOC members agreed to keep group as is for now and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be tasked to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at an upcoming teleconference. | Approved
#4 | Information and Communication Technology Policy Working Group - Framework Working Group recommended for the ICT Policy Working Group to transition to a Community of Practice. PSCIOC members agreed to reach out to ICT Policy Working Group Co-Chairs and get a better understanding of their current work and identify areas of potential collaboration and support in order to determine next steps. PSCIOC members to have a further discussion on this item at an upcoming teleconference. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html