## Action Items
| PSCIOC ACTION ITEMS |  |  |  | Updated on August 26, 2019
|  | Next PSCIOC Meeting: | September 26th, 2019
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSCIOC Teleconference of August 8, 2019
#1A | NCSIP: Ontario representative will present on the Ontario journey to the Cloud, including onboarding and assessments of technical requirements, at the next PSCIOC teleconference. (as per request from the Feb meeting) | NCSIP Chair | August 8th | Pending | Item to be scheduled at an upcoming teleconference/meeting.
#1B | NCSIP: to report back on the access and release of information as it pertains to security. | NCSIP Chair | August 8th | Pending | Item to be scheduled at an upcoming teleconference/meeting.
#1C | NCSIP to do a jurisdictional scan across the country on ISO compliance and report back to PSCIOC at an upcoming teleconference. | NCSIP Chair | August 8th | Pending | Item to be scheduled at an upcoming teleconference/meeting.
PSCIOC Teleconference of June 10, 2019
#1C | Cloud WG and IT Procurement WG members to be invited to attend this session in September (via teleconference). Members can also invite their team members to join this session. | ICCS | June 10th | Underway | Members of Cloud and ICT WG invited to AWS session at the September meeting (via teleconference).
#2 | Kathryn Bulko to report back on the endorsement of the Digital Principles (as per the review underway by MISA of the current TBS digital principles and those of other countries: Australia, UK, USA, NZ, Belgium, Sweden, Netherlands.) | IT Procurement WG Chair | June 10th | Pending | Update at the November PSCIOC teleconference
#3A | ICCS to connect with TBS to discuss conversation with Infrastructure Canada on a presentation on Smart Cities. (original ask tabled at the Whitehorse 2018 meeting for a presentation on Smart Cities - information on best practices.) | ICCS & TBS | June 10th | Pending | Presentation at an upcoming PSCIOC teleconference (due to federal election).
PSCIOC Teleconference of April 16, 2019
#1B | Cloud Working Group Co-Chairs to report back on the results of the Cloud Benefits Realization Survey at the next PSCIOC meeting. | Cloud Working Group Co-Chairs | April 16th | Underway | Item on the September 2019 meeting agenda.
#2A | ICCS to schedule a meeting between PSCIOC Co-Chairs and Microsoft to discuss outcome of Ottawa meeting. Context: (John Weigelt, Microsoft, will look into the following issues and get back to the members: a) Licensing – more clarity around negotiations, transparency, large vs small, equitable contracts; b) Unified support; c) Challenges with budgeting; d) Language Localization; e) Issues with bureaucracy around services ; f) How to and easier access Microsoft engineers; and g) Opportunity for better communication with CIOs across the country on an ongoing basis.) | PSCIOC Co-Chairs and ICCS | April 16th | Completed | ICCS meeting between Co-Chairs and Microsoft on June 11. Microsoft to report back to PSCIOC Co-Chairs. ICCS followed up, awaiting response from Microsoft.
PSCIOC Meeting of February 28, 2019 (Ottawa)
#3 | PSCIOC Financial Matters: Members agreed on a discussion at the September 2019 meeting which would include: an explanation of the current PSCIOC funding formula and in-kind services provided by TBS which may need revisiting including in-kind support from Ontario that was withdrawn a few years ago. | PSCIOC Treasurer | Feb 28, 2019 | Underway | Item on the September 2019 meeting agenda.
#4 | Alignment with JC Logic Model: A discussion about PSCIOC alignment with Joint Council priorities and its working groups will be brought back to a future meeting of the PSCIOC. | PSCIOC Co-Chairs / Cathy Kealey | Feb 28, 2019 | Underway | Item on the JC September meeting (Joint Councils).
#6B | PSCIOC members to have a further discussion around funding and FPTM collaboration to support and advance a specific project / initiative / priority for the Council (i.e. Yukon’s suggestion of a smart phone app or other to be identified initiative / priority). | PSCIOC Co-Chairs / Yukon | Feb 28, 2019 | Underway | Discussion on the direction of the Councils at the JC meeting in September.
PSCIOC Teleconference of November 21, 2018
#2A | The ICT Policy WG Co-Chairs to share proposed topics of interest that the group can work on at an upcoming PSCIOC meeting/teleconference. | Keith Douglass and Michael Nielsen | 2018-11-21 | Pending | Further update required by JC Strategic Policy Analyst at an upcoming meeting
PSCIOC Meeting of September 27, 2018 (Whitehorse)
#1 | Artificial Intelligence (AI): PSCIOC to continue the discussion on Artificial Intelligence (focus on used cases and how to leverage AI to be more efficient) at an upcoming teleconference/meeting. | PSCIOC Co-Chairs/Members | 2018-09-27 | Underway | Item scheduled at the September meeting - Learning Event agenda
#8C | Trust Traveller Project pilot: to be included in an upcoming teleconference/meeting agenda. | PSCIOC members | 2018-09-27 | Pending | Item to be scheduled at an upcoming teleconference/meeting.
#8D | Phoenix Pay System: Discussion on lessons learned around the Phoenix pay system to be included in the next in person meeting agenda. | TBS | 2018-09-27 | Pending | Presentation by TBS at an upcoming PSCIOC teleconference (due to federal election).
PSCIOC Meeting of February 22, 2018 (Toronto)
#1C | Information Management (IM) Sub-Committee - Framework Working Group recommended for the IM Sub-Committee to transition to a Community of Practice. PSCIOC members agreed to keep group as is for now and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be tasked to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at an upcoming teleconference. | PSCIOC Co-Chairs/Members | 2018-02-22 | Underway | Decision on status of this group on the September 2019 agenda, recommendation by JC strategic policy analyst.

## Decisions
DECISIONS
| ITEM | STATUS
#1 | PSCIOC Members confirmed Tracy Wood as the new PSCIOC Co-Chair, starting on June 1st, 2019.
#2 | PSCIOC Members confirmed Bonnie Schmidt as the new PSCIOC Treasurer starting in August 2019.
#3 | PSCIOC Members approved the Cloud Working Group Workplan and updated Terms of Reference with requested amendment.
PSCIOC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | As FPTM CIOs, we agree to go to our own jurisdiction and deal with the http issue (moving to https). Jurisdictions can use the federal tools available. Members to advise their jurisdiction that this was brought up by NCSIP and we need to take action to clean this up. NCSIP to track the inventories and progress as part of the artifacts they are collecting. | Approved
#2 | PSCIOC members agreed for MISA to be able to share information from the jurisdictional information sharing collected for each in person meeting, however confidential information (or what is considered sensitive information) can only be shared if the jurisdictional member (author) is consulted and approval is given to share. | Approved
PSCIOC MEETING OF FEBRUARY 22, 2018
#1 | PSCIOC members approved the request by NCSIP to fund four day meetings twice a year, up to a maximum of 8 meeting days per year. (The current policy only allows up to a maximum of 6 meeting days per year.) This approval only applies to NCSIP and not to other groups of PSCIOC. | Approved
#2 | NCSIP: General agreement (access and support) in principle by members on all the recommendations by NCSIP. | Approved
#3 | Information Management (IM) Sub-Committee - Framework Working Group recommended for the IM Sub-Committee to transition to a Community of Practice. PSCIOC members agreed to keep group as is for now and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be tasked to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at an upcoming teleconference. | Approved
#4 | Information and Communication Technology Policy Working Group - Framework Working Group recommended for the ICT Policy Working Group to transition to a Community of Practice. PSCIOC members agreed to reach out to ICT Policy Working Group Co-Chairs and get a better understanding of their current work and identify areas of potential collaboration and support in order to determine next steps. PSCIOC members to have a further discussion on this item at an upcoming teleconference. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html