## Action Items
| PSCIOC ACTION ITEMS |  |  |  | Updated Sept 1, 2022
|  | Next PSCIOC meeting: | 2022-09-29
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSCIOC Meeting of August 11, 2022
#1A | Paul Wagner to provide the list of Ministers and DMs at the federal level related to digital identity. | TBS | Aug-11-2022 | Pending
#1B | BC to share the agenda and material for the January Ministers’ and November DMs’ meeting with PSCIOC. | BC | Aug-11-2022 | Underway | Item on the September meeting agenda
#2 | SWAT Team to report back on a plan with funding model related to standing up a digital Identity program office. | Digital ID SWAT Team | Aug-11-2022 | Underway | Item on the September meeting agenda
#3 | NCSIP Chair to present the proposal and the request for funding related to the talent and the compensation at the September PSCIOC meeting. | NCSIP Chair | Aug-11-2022 | Underway | Item on the September meeting agenda
PSCIOC Meeting of June 23, 2022
MS Office 365 Working Group
#1A | MS Office 365 Chair to share the deck presentation with members via ICCS Secretariat. | MS O365 WG | 2022-06-23 | Completed
#1B | Zelko Holjevac to discuss with the MS O365 Working Group a request from PSCIOC on drafting recommendations or identifying the best approach on how to create a unified public sector voice when dealing with MS and other vendors. Zelko to report back to PSCIOC. | MS O365 WG | 2022-06-23 | Pending | Update at an upcoming meeting.
#1C | TBS to inquire within the federal government about the SaaS products that are built in and that can be extended to the P/Ts and report back to PSCIOC. | TBS | 2022-06-23 | Pending | Update at an upcoming meeting.
PSCIOC Meeting of February 16, 2022
#1 | British Columbia (Matt Reed, Rhianna Begley) to provide further information on open data and open information as it relates to FOIPPA at an upcoming PSCIOC meeting. | Mat Reed, Rhianna Begley | 2022-02-16 | Pending | Update at an upcoming meeting.
#2A | PSCIOC members want to explore the development and maintenance of an information sharing (information management) platform that would gather all the information that is collected from jurisdictional information sharing (twice a year), research on priority topics (including monthly research reports), and results of jurisdictional scans undertaken by PSCIOC members. Objectives of the information sharing platform: 1. Chat function and/or communication channel for members to pose quick questions on specific items. 2. Collection of jurisdictional information sharing and reporting on key insights (information sharing analysis). 3. Ability to run jurisdictional scans (for quicker response and quick access to results). This will serve as a repository of what jurisdictions are doing, from the numerous questions asked by members, (for example a Microsoft agreement, who is using open source, multivendor in the telecommunication, etc.). If a member has a specific question, it would a) know who to ask and b) get the answer by searching the inventory or communicating with specific jurisdictions. And if they have more specific questions or require more information it could use the chat function. 4. Opportunity to undertake specific research commissioned and funded by PSCIOC members to drive decision making conversations. | Information Management Task Force and the ICCS | 2022-02-16 | Underway | First meeting of the working group took place in April. Second meeting to review scope of work scheduled for July 2022. Update at the August 11th meeting. Pending further discussion with IM Task Team.
#2C | TBS to report back on how PTMs can access digital academy courses delivered by the Digital Academy. | TBS | 2022-02-16 | Pending | TBS to provide further details
#3 | TBS to provide clarity and guidance on the roles that other entities play (digital ecosystem) in the digital identity space, such as DIACC, CIO Strategy Council, vendors and other internal and external stakeholders. | TBS | 2022-02-16 | Pending | Digital ID program discussion at Joint Councils.
PSCIOC Meeting of October 27, 2021
#1 | Peter Watkins to report back to Joint Councils on how to move forward discussion on modernizing business registration to support economic recovery (digital proof of business registration and ownership) as it relates to work on digital identity and engaging other partners in this work such as corporate registrars. Peter to report back on the development of a shared narrative that could be established at the most senior levels across multiple jurisdictions. A shared narrative involving small and medium size Canadian business (digital proof of business registration and ownership) as a matter of economic development and trade. | Digital ID Program Executive | 2021-10-27 | Underway | Peter to report back on this item at the September 2022 meeting.
PSCIOC Meeting of April 28, 2021
#1A | PSCIOC members asked for clarity around the role and work of the CIO Strategy Councils as it relates to the Joint Councils’ Digital Identity Program. PSCIOC Co-Chairs to have discussion on this matter and report back to PSCIOC members at an upcoming meeting. | PSCIOC Co-Chairs | Apr-28-21 | Pending | Digital ID Program Executive to report back on this item at JC. Part of a previous ask tabled at JC. Recent request by PSCIOC (Feb 2022) for TBS to provide this information.
PSCIOC Meeting of March 31, 2021
Cloud Working Group
#2A | The ICCS to work with the PSCIOC P/T Co-Chair and the Cloud WG Co-Chair offices to schedule the one-on-one meetings with the PSCIOC members to discuss the mandate of Cloud WG. | ICCS / PSCIOC P/T Chair | 2021-03-31 | On Hold | Jurisdictional consultations are almost complete but on hold due to Cloud WG chair on leave. TBS to identify rep to advance this work.
PSCIOC Meeting of October 22, 2020
#2 | TBS to report back at a future PSCIOC meeting on the federal government perspective related to Cabinet and Treasury Board memos - digital signature. | PSCIOC Co-Chair, TBS | 2020-10-22 | Pending | Update at an upcoming meeting.

## Decisions
DECISIONS
| ITEM | STATUS
PSCIOC MEETING OF FEBRUARY 16, 2022
#1 | Record of Decision of October 27, 2020 PSCIOC meeting approved without changes. | Approved
#1 | Agenda of February 16 Meeting, 2022 PSCIOC meeting approved without changes. | Approved
PSCIOC MEETING OF OCTOBER 27, 2021
#1 | Record of Decision of February 24, 2021 PSCIOC meeting approved without changes. | Approved
#1 | Agenda of October 27 Meeting, 2021 PSCIOC meeting approved without changes. | Approved
PSCIOC Meeting of August 12, 2021
#1 | PSCIOC Members decided to capture in the RoD only relevant links or comments that are made in the MS Teams chat, and those that are signaled by members. | Approved
PSCIOC Meeting of May 19, 2021
#1 | PSCIOC members approved for Tracy Wood to serve an additional year as PSCIOC P/T Co-Chair, until June 1, 2022. | Approved
PSCIOC Meeting of March 31, 2021
#1 | PSCIOC members approved the proposed IT Procurement CoP Terms of Reference | Approved
#1 | The P/T Co-Chair and Cloud WG Co-Chair to meet with PSCIOC members to discuss the mandate and future of the Cloud Working Group. | Approved
PSCIOC Meeting of February 24, 2021
#1 | Record of Decision of September 23, 2020 PSCIOC meeting approved without changes. | Approved
#1 | Agenda of February 24 Meeting, 2021 PSCIOC meeting approved without changes. | Approved
PSCIOC Meeting of November 5 2020
#1 | PSCIOC members approved the ICT Community of Practice Terms of Reference. | Approved
PSCIOC MEETING OF JUNE 4 2020
#1 | PSCIOC Members agreed on moving from weekly PSCIOC meeting to bi-weekly meetings until further notice. | Approved
PSCIOC MEETING OF MAY 21 2020
#1 | PSCIOC Members approved Zelko Holjevac as the new Lead of the Microsoft Office 365 group. | Approved
PSCIOC MEETING OF APRIL 24 2020
#1 | PSCIOC members decided to invite the PSSDC members at their April 30th meeting to discuss the Business Resumption Planning. | Approved
PSCIOC MEETING OF MARCH 24, 2020
#1 | Members approved the decision of weekly PSCIOC meetings to discuss the work during the COVID-19 pandemic. | Approved
PSCIOC MEETING OF FEBRUARY 26, 2020
#1 | Record of Decision of September 26, 2019, PSCIOC meeting in Winnipeg approved without changes. | Approved
#2 | Agenda of February 26th, 2020 PSCIOC meeting approved. | Approved
#3 | CJ Ritchie moved that the Data Driven Intelligence (DDI) Group be moved to the Joint Councils; seconded Natasha Clarke. | Approved
#4 | Catherine Desgagnés-Belzil moved that the Service to Business Working Group be moved to the Joint Councils; seconded Natasha Clarke. | Approved
PSCIOC TELECONFERENCE OF JANUARY 17, 2020
#1 | PSCIOC members were in support of adopting recommendation #3 to adjust the PSCIOC annual contributions to a phased-in approach. Adjustment would take effect starting fiscal period 2020-2021. | Approved
PSCIOC MEETING OF SEPTEMBER 26, 2019 (WINNIPEG)
#1 | Record of Decision of February 28th, 2019, PSCIOC meeting in Ottawa approved without changes. | Approved
#2 | Agenda of September 26th, 2019 PSCIOC meeting approved. | Approved
PSCIOC TELECONFERENCE OF AUGUST8, 2019
#1 | Record of Decision from June 10 Teleconference were approved | Approved
#1 | PSCIOC Members confirmed Tracy Wood as the new PSCIOC Co-Chair, starting on June 1st, 2019. | Approved
#2 | PSCIOC Members confirmed Bonnie Schmidt as the new PSCIOC Treasurer starting in August 2019. | Approved
#3 | PSCIOC Members approved the Cloud Working Group Workplan and updated Terms of Reference with requested amendment. | Approved
PSCIOC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | As FPTM CIOs, we agree to go to our own jurisdiction and deal with the http issue (moving to https). Jurisdictions can use the federal tools available. Members to advise their jurisdiction that this was brought up by NCSIP and we need to take action to clean this up. NCSIP to track the inventories and progress as part of the artifacts they are collecting. | Approved
#2 | PSCIOC members agreed for MISA to be able to share information from the jurisdictional information sharing collected for each in person meeting, however confidential information (or what is considered sensitive information) can only be shared if the jurisdictional member (author) is consulted and approval is given to share. | Approved
PSCIOC MEETING OF FEBRUARY 22, 2018
#1 | PSCIOC members approved the request by NCSIP to fund four day meetings twice a year, up to a maximum of 8 meeting days per year. (The current policy only allows up to a maximum of 6 meeting days per year.) This approval only applies to NCSIP and not to other groups of PSCIOC. | Approved
#2 | NCSIP: General agreement (access and support) in principle by members on all the recommendations by NCSIP. | Approved
#3 | Information Management (IM) Sub-Committee - Framework Working Group recommended for the IM Sub-Committee to transition to a Community of Practice. PSCIOC members agreed to keep group as is for now and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be tasked to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at an upcoming teleconference. | Approved
#4 | Information and Communication Technology Policy Working Group - Framework Working Group recommended for the ICT Policy Working Group to transition to a Community of Practice. PSCIOC members agreed to reach out to ICT Policy Working Group Co-Chairs and get a better understanding of their current work and identify areas of potential collaboration and support in order to determine next steps. PSCIOC members to have a further discussion on this item at an upcoming teleconference. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html