## Action Items
| PSSDC ACTION ITEMS |  |  |  | Last updated: Feb 12, 2021
|  | Next PSSDC Meeting | February 25, 2021
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSSDC Meeting of January 21, 2021
| PSSDC member from NS to provide an update on the virtual check in system at a future PSSDC meeting. | Nova Scotia | 2021-01-21 | Pending | ICCS To confirm update for a future PSSDC meeting.
| PSSDC member from BC to provide an update on the Appointment App that BC is developing at a future PSSDC meeting. | British Columbia | 2021-01-21 | Pending | ICCS To confirm update for a future PSSDC meeting.
PSSDC Meeting of December 4, 2020
#1 | IRCC Showcase presentation: IRCC to provide further information related to challenges from a delivery and design perspective on chatbots. | IRCC | 2020-12-04 | Pending | ICCS to follow up with Contact Centre CoP.
#2 | PSSDC scan results: Research Analyst to connect with ESDC/Service Canada to learn more about the communication tool built in service design and delivery and about the services that have been built during the pandemic to inform the management of service delivery in the wake of pandemic from those three surveys conducted by ESDC and report back to the PSSDC members. | Research Analyst | 2020-12-04 | Pending | Research Analyst to report back.
PSSDC Meeting of November 4, 2020
PSSDC Info Sharing and Strategic Opportunities
#1A | The Research Analyst and Research Committee to report back to Joint Councils and PSSDC on research they have come across (including national and international trends) related to the Councils’ priorities that would provide insights to the work of the Councils. | Research Committee Co-Chairs and Research Analyst | 2020-11-04 | Pending | Item to be scheduled for a future PSSDC meeting
#2 | The Research Analyst to develop a prototype of the new PSSDC information sharing master document to be available for the February meeting along with the analysis of the information sharing findings. | Research Analyst | 2020-11-04 | Underway | Item to be scheduled for the February 25th, 2021 PSSDC meeting
PSSDC Meeting of September 25, 2020
PSSDC Strategic Direction
#2 | PSSDC Next Steps as discussed at the meeting: #2F: Establish a Client-Centric Design Community of Practice to share jurisdictions’ knowledge, tools and resources. Call out for FPTM co-chairs of the JC Client-Centred Design Community of Practice. | PSSDC Co-Chairs / ICCS | 2020-09-24 | Completed | CCS Design/Experience CoP being established. Group will report to JC.
#3 | Sunset the current JC Client Centric Services Working Group once a digital, user-friendly maturity model and user guide have been developed. | CCS WG | 2020-09-24 | Underway | Item on PSSDC February 25th agenda.
#4 | Request for follow up session with Pia Andrews in fall 2020. | ICCS / PSSDC Co-Chairs | 2020-09-24 | Pending | Planning for follow up session in December 2020 with JC.
#5

## Decisions
DECISIONS
| ITEM | STATUS
PSSDC MEETING OF SEPTEMBER 3, 2020
#1 | Members agreed to move the Service to Business under the Joint Councils, with the note that PSSDC will provide direction to the group on future activities. | Approved
PSSDC MEETING OF FEBRUARY 26, 2020
#1 | The Record of Decision from the PSSDC September 26th, 2019 meeting has been approved without changes. | Approved
#2 | The PSSDC February 26th, 2020 meeting agenda has been approved without changes. | Approved
PSSDC TELECONFERENCE OF NOVEMBER 15, 2019
#1 | PSSDC members approved the updated Service to Business Working Group Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 26, 2019
#1 | The Record of Decision from the PSSDC February 28th, 2019 meeting approved without changes. | Approved
#2 | The PSSDC September 26th, 2019 meeting agenda approved without changes. | Approved
#3 | PSSDC Members approved recommendation from the Service to Business Working Group to amend its Terms of Reference to include a second P/T Co-Chair. | Approved
#4 | PSSDC members approved Mark Burns as incoming P/T Co-Chair. The term of the P/T co-chair is for a period of two years. | Approved
PSSDC MEETING OF FEBRUARY 28, 2019
#1 | The Record of Decision from September 27th, 2018 PSSDC meeting in Whitehorse approved without changes. | Approved
#2 | The February 28th, 2019 PSSDC meeting agenda approved without changes. | Approved
#3 | The Service Network Collaboration Working Group to be sunset. | Approved
PSSDC TELECONFERENCE DECEMBER 10TH, 2018
#1 | PSSDC Members approved the Service to Business Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | Approval of the Terms of Reference – Mark Burns moved the approval of the terms of reference for the Data Driven Intelligence Working Group; Gillian Latham seconded. | Approved
#2 | Development of a DDI Playbook – Beverly Dicks moved the approval of development of a Data Driven Intelligence Playbook; Jackie Stankey seconded. | Approved
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC P/T Co-Chair's position: PSSDC members approved a one year extension of the P/T Co-Chair's (Natasha Clarke) position from Sept. 2018 to Sept. 2019. The P/T Co-Chair position would end at the Sept. 2019 PSSDC meeting. | Approved
#2 | Data Driven Intelligence: PSSDC members adopted a recommendation for DDI to become a priority of the PSSDC. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html