## Action Items
| PSSDC ACTION ITEMS |  |  |  | Last updated: Feb 14, 2023
|  | Next PSSDC Meeting | February 22nd, 2023
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSSDC Meeting of January 31, 2023
#1 | British Columbia and Canada Revenue Agency to share with members, via the ICCS Secretariat, the documentation that they have related to the RPA (bots) and the system that are compatible for that. | BC, CRA | 2023-01-31 | Pending | ICCS to follow up with BC and CRA.
#2 | The ICCS to share the updated PSSDC members’ annual contributions 2023/2024 with members when available. | ICCS Secretariat | 2023-01-31 | Completed
PSSDC Meeting of December 13, 2022
#1 | The PSSDC Co-Chairs to send the call out to the Council’s members for the membership related to the two created working groups: 1a. Unclaimed Benefits and 1b. Service Design. | PSSDC Co-Chairs | 2022-12-12 | Pending
PSSDC Meeting of November 8, 2022
#1 | PSSDC Co-Chairs to report back to PSSDC members around the creation of a new data science community of practice and/or ways of moving this discussion forward. | PSSDC Co-Chairs | 2022-11-08 | Pending | PSSDC Co-Chairs to provide direction on this item - related to Data Science, AI and RPA priority.
PSSDC Meeting of September 29, 2022
#1B | Pathos AI to be invited to a future meeting to showcase their progress related to measuring citizens’ emotional engagement. | Pathos AI | 2022-09-29 | Pending | Item on bring forward agenda - related to AI and RPA priority.
#2 | James Gilbert recommended for PSSDC to add to the bring forward agenda a discussion on shared service delivery across jurisdictions; themes to consider related to invisible visibility and a proactive way to look at accessibility. | PSSDC co-chairs/ ICCS / Research Committee | 2022-09-29 | Pending | Item on bring forward agenda
#4 | ISC (Lori Doran) to report back to the PSSDC on ISC’s jurisdictional scan results and proposed scope for the creation of a working group to address TRC’s Call to Action #17 | Indigenous Services Canada (Lori Doran) | 2022-09-29 | Underway | Item on the February 2023 meeting agenda
PSSDC Meeting of June 6, 2022
#1B | PSSDC Co-Chairs to find out if there is a working group on CX Research, and if not, for PSSDC to consider creating a working group or community of practice to share information and opportunity for inter-jurisdictional collaboration. | PSSDC co-chairs | 2022-06-06 | Pending
PSSDC Meeting of May 3, 2022
#1A | John Houweling to share the Data maturity model with PSSDC members when the work on that is completed. | John Houweling | 2022-05-03 | Pending | Municipality will share when ready.
#1B | John Houweling and Andrew Satterthwaite to be invited to a future PSSDC meeting to provide progress on the work they are doing in building a data informed organization. | John Houweling and Andrew Satterthwaite | 2022-05-03 | Pending | Item for an upcoming meeting - related to Data Science, AI and RPA priority.

## Decisions
DECISIONS
| ITEM | STATUS
PSSDC IN-PERSON MEETING OF SEPTEMBER 29, 2022
#1 | Record of Decision of February 17, 2022, PSSDC meeting approved without changes. | Approved
#2 | Agenda of September 29, 2022, PSSDC meeting approved without changes. | Approved
#3 | PSSDC members’ endorsement of Sheila Robinson, Assistant Deputy Minister, Service BC, as the new PSSDC P/T Co-Chair for a tenure of two years. (Sept 2022 to 2024). | Approved
PSSDC VIRTUAL MEETING OF FEBRUARY 18, 2022
#1 | Record of Decision of October 28, 2021 PSSDC meeting approved without changes. | Approved
#2 | Agenda of February 18, 2022 PSSDC meeting approved without changes | Approved
PSSDC VIRTUAL MEETING OF OCTOBER 28, 2021
#1 | Record of Decision of February 25, 2021 PSSDC meeting approved without changes. | Approved
#2 | Agenda of October 28, 2021 PSSDC meeting approved without changes | Approved
#3 | PSSDC Members approved the new format of the information sharing. | Approved
PSSDC MEETING OF FEBRUARY 25, 2021
#1 | Record of Decision of September 24, 2020 PSSDC meeting approved without changes. | Approved
#2 | Agenda of February 25, 2021 PSSDC meeting approved. | Approved
#3 | PSSDC Members endorsed the one-year extension for Mark Burns to serve as P/T co-chair until September 2022. | Approved
PSSDC MEETING OF SEPTEMBER 3, 2020
#1 | Members agreed to move the Service to Business under the Joint Councils, with the note that PSSDC will provide direction to the group on future activities. | Approved
PSSDC MEETING OF FEBRUARY 26, 2020
#1 | The Record of Decision from the PSSDC September 26th, 2019 meeting has been approved without changes. | Approved
#2 | The PSSDC February 26th, 2020 meeting agenda has been approved without changes. | Approved
PSSDC TELECONFERENCE OF NOVEMBER 15, 2019
#1 | PSSDC members approved the updated Service to Business Working Group Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 26, 2019
#1 | The Record of Decision from the PSSDC February 28th, 2019 meeting approved without changes. | Approved
#2 | The PSSDC September 26th, 2019 meeting agenda approved without changes. | Approved
#3 | PSSDC Members approved recommendation from the Service to Business Working Group to amend its Terms of Reference to include a second P/T Co-Chair. | Approved
#4 | PSSDC members approved Mark Burns as incoming P/T Co-Chair. The term of the P/T co-chair is for a period of two years. | Approved
PSSDC MEETING OF FEBRUARY 28, 2019
#1 | The Record of Decision from September 27th, 2018 PSSDC meeting in Whitehorse approved without changes. | Approved
#2 | The February 28th, 2019 PSSDC meeting agenda approved without changes. | Approved
#3 | The Service Network Collaboration Working Group to be sunset. | Approved
PSSDC TELECONFERENCE DECEMBER 10TH, 2018
#1 | PSSDC Members approved the Service to Business Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | Approval of the Terms of Reference – Mark Burns moved the approval of the terms of reference for the Data Driven Intelligence Working Group; Gillian Latham seconded. | Approved
#2 | Development of a DDI Playbook – Beverly Dicks moved the approval of development of a Data Driven Intelligence Playbook; Jackie Stankey seconded. | Approved
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC P/T Co-Chair's position: PSSDC members approved a one year extension of the P/T Co-Chair's (Natasha Clarke) position from Sept. 2018 to Sept. 2019. The P/T Co-Chair position would end at the Sept. 2019 PSSDC meeting. | Approved
#2 | Data Driven Intelligence: PSSDC members adopted a recommendation for DDI to become a priority of the PSSDC. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html