## Action Items
| PSSDC ACTION ITEMS |  |  |  | Last updated: September 6, 2019
|  | Next PSSDC Meeting: | September 26, 2019
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSSDC Teleconference, June 10th 2019
Data Driven Intelligence Working Group
#1 | DDI Working Group to report back on next steps around the work of the group. | DDI Co-Chairs | 2019-06-10 | Underway | Item on the PSSDC September meeting agenda
Indigenous Services
#2 | PSSDC Co-Chairs and Hillary Thatcher to report back on this session at the August teleconference. | PSSDC Co-Chairs & ISC | 2019-06-10 | Underway | Item on the PSSDC September meeting agenda
Contact Centres
#3 | ICCS to send PSSDC members email seeking their approval to establish a Contact Centre Community of Practice. | ICCS | 2019-06-10 | Completed / Follow up | CoP to report back at the teleconference in November.
Jurisdictional Information Sharing Template
#4B | The Joint Councils Strategic Policy Analyst to provide a dashboard format for information sharing analysis (template including all four questions). | Joint Councils Strategic Policy Analyst | 2019-06-10 | Pending | Information sharing analysis will be provided in October.
PSSDC Teleconference, April 8th 2019
Services to Indigenous Populations
#1B | PSSDC Co-Chairs and ISC to identify leads from Indigenous organizations to be invited to this discussion. ICCS to assist in sending invitations and working on logistics for September meeting. | PSSDC Co-Chairs and ISC | 2019-04-08 | Underway | Item on the PSSDC September meeting agenda
PSSDC Meeting of February 2019 (Ottawa)
Service to Business Working Group
#2C | Service to Business Working Group Co-Chairs to collect and reflect on members’ feedback and to report back to PSSDC with recommendations on defined future activities. | Anne Matthews, Pirth Singh | 2019-02-28 | Underway | Item on the PSSDC September meeting agenda
Strategic Discussion on PSSDC Priorities
#3D | Confirm approach and next steps to develop a problem statement/case for change to address the legislative and data sharing barriers impeding the advancement of Joint Councils and PSSDC priorities. | PSSDC Co-Chairs | 2019-02-28 | Underway | Item on the JC September meeting agenda
BC Pilot: Open Source (The Q, Analytics, Business Intelligence – Enablers for BC)
#4A | Ron Hinshaw to share with the PSSDC members the analysis on the HR component via ICCS Secretariat. | Ron Hinshaw | 2019-02-28 | Pending | BC to provide information at a later date.
PSSDC Meeting of September 27, 2018 (Whitehorse)
Data Driven Intelligence Working Group
#3A | Members were asked to look at how the EVI tool could be used in their jurisdictions. Further discussion on the EVI tool to be scheduled at an upcoming teleconference or meeting. | PSSDC Members | 2018-09-27 | Pending | DDI Co-Chairs to provide information at an upcoming meeting/teleconference.
Research Committee
#5 | Members requested the Joint Councils Research Committee to review the national results of CF8 and provide insights or recommendations on areas of focus (unpacking results) for PSSDC to have a meaningful conversation on this topic. | Richard Dalpé, Guy Gordon, Research Committee Co-Chairs | 2018-09-27 | Pending | ICCS has followed up with Research Committee. The Research Committee to follow up on this at an upcoming meeting/teleconference.

## Decisions
DECISIONS
| ITEM | STATUS
PSSDC MEETING OF FEBRUARY 28, 2019
#1 | The Record of Decision from September 27th, 2018 PSSDC meeting in Whitehorse approved without changes.
#2 | The February 28th, 2019 PSSDC meeting agenda approved without changes.
#3 | The Service Network Collaboration Working Group to be sunset.
PSSDC TELECONFERENCE DECEMBER 10TH, 2018
#1 | PSSDC Members approved the Service to Business Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | Approval of the Terms of Reference – Mark Burns moved the approval of the terms of reference for the Data Driven Intelligence Working Group; Gillian Latham seconded. | Approved
#2 | Development of a DDI Playbook – Beverly Dicks moved the approval of development of a Data Driven Intelligence Playbook; Jackie Stankey seconded. | Approved
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC P/T Co-Chair's position: PSSDC members approved a one year extension of the P/T Co-Chair's (Natasha Clarke) position from Sept. 2018 to Sept. 2019. The P/T Co-Chair position would end at the Sept. 2019 PSSDC meeting. | Approved
#2 | Data Driven Intelligence: PSSDC members adopted a recommendation for DDI to become a priority of the PSSDC. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html