## Action Items
| PSSDC ACTION ITEMS |  |  |  | Last updated: Feb 12, 2020
|  | Next PSSDC Meeting | Wednesday, February 26, 2020
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSSDC Teleconference of November 15th, 2019
Service to Business Working Group
#1A | Service to Business Working Group to present a summary of the survey undertaken by ISED and Stats Canada. | Service to Business Working Group Co-Chairs | 2019-11-15 | Underway | Report back at the Feb 26, 2020 meeting
#1B | Service to Business Working Group Co-Chairs to report back on diagnostics and voice of the client related to service to business issues and scoping out solutions. | Service to Business Working Group Co-Chairs | 2019-11-15 | Underway | Report back at the Feb 26, 2020 meeting
Contact Centre Community of Practice
#2A | Contact Centre Community of Practice to share the Terms of Reference and membership list via the ICCS. | Contact Centre Community of Practice Co-Chairs | 2019-11-15 | Pending | Follow up at an upcoming teleconference / meeting.
#2B | Contact Centre Community of Practice to report back on their work at a future PSSDC meeting. | Contact Centre Community of Practice Co-Chairs | 2019-11-15 | Pending | Follow up at an upcoming teleconference / meeting.
Data Driven Intelligence Working Group
#3 | Data Driven Intelligence Working Group to share the DDI Working Group research proposal in early January 2020. | Data Driven Intelligence Working Group Co-Chairs | 2019-11-15 | Underway | Report back at the Feb 26, 2020 Joint Councils meeting
Governance
#4 | Service to Business and Data Driven Intelligence Working Groups to discuss with their respective membership the pros and cons of moving the S2B and DDI under Joint Councils and report back to the PSSDC at the next teleconference. | Service to Business and Data Driven Intelligence Working Group Co-Chairs | 2019-11-15 | Pending | Follow up at an upcoming teleconference / meeting.
PSSDC Meeting of September 26, 2019 (Winnipeg)
Indigenous Services Canada
#3 | ISC leads to come back to the table with some crunchy and tangible things that we can collaborate on and how to create partnerships with communities to advance this work. | Indigenous Services Canada Leads | 2019-09-26 | Pending | Follow up at an upcoming teleconference / meeting.
Best Practices Showcase (IRCC - Measuring the Impact of Service Design Changes)
#4 | IRCC invited to provide a progress report at an upcoming meeting on their work/results related to measuring the impact of service design changes. | PSSDC Member representing IRCC | 2019-09-26 | Pending | Follow up at an upcoming teleconference / meeting.
PSSDC Teleconference, June 10, 2019
Jurisdictional Information Sharing Template
#4B | The Joint Councils Research Analyst to provide a dashboard format for information sharing analysis (template including all four questions). | Joint Councils Strategic Policy Analyst | 2019-06-10 | Underway | PSSDC Research Analyst to provide information sharing analysis at the Feb meeting.
PSSDC Meeting of September 27, 2018 (Whitehorse)
Research Committee
#5 | Members requested the Joint Councils Research Committee to review the national results of CF8 and provide insights or recommendations on areas of focus (unpacking results) for PSSDC to have a meaningful conversation on this topic. | Richard Dalpé, Guy Gordon, Research Committee Co-Chairs | 2018-09-27 | Pending | ICCS has followed up with Research Committee. The Research Committee to follow up on this at an upcoming meeting/teleconference.

## Decisions
DECISIONS
| ITEM | STATUS
PSSDC TELECONFERENCE OF NOVEMBER 15, 2019
#1 | PSSDC members approved the updated Service to Business Working Group Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 26, 2019
#1 | The Record of Decision from the PSSDC February 28th, 2019 meeting approved without changes. | Approved
#2 | The PSSDC September 26th, 2019 meeting agenda approved without changes. | Approved
#3 | PSSDC Members approved recommendation from the Service to Business Working Group to amend its Terms of Reference to include a second P/T Co-Chair. | Approved
#4 | PSSDC members approved Mark Burns as incoming P/T Co-Chair. The term of the P/T co-chair is for a period of two years. | Approved
PSSDC MEETING OF FEBRUARY 28, 2019
#1 | The Record of Decision from September 27th, 2018 PSSDC meeting in Whitehorse approved without changes. | Approved
#2 | The February 28th, 2019 PSSDC meeting agenda approved without changes. | Approved
#3 | The Service Network Collaboration Working Group to be sunset. | Approved
PSSDC TELECONFERENCE DECEMBER 10TH, 2018
#1 | PSSDC Members approved the Service to Business Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | Approval of the Terms of Reference – Mark Burns moved the approval of the terms of reference for the Data Driven Intelligence Working Group; Gillian Latham seconded. | Approved
#2 | Development of a DDI Playbook – Beverly Dicks moved the approval of development of a Data Driven Intelligence Playbook; Jackie Stankey seconded. | Approved
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC P/T Co-Chair's position: PSSDC members approved a one year extension of the P/T Co-Chair's (Natasha Clarke) position from Sept. 2018 to Sept. 2019. The P/T Co-Chair position would end at the Sept. 2019 PSSDC meeting. | Approved
#2 | Data Driven Intelligence: PSSDC members adopted a recommendation for DDI to become a priority of the PSSDC. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html