## Action Items
| PSSDC ACTION ITEMS |  |  |  | Last updated: February 7, 2019
|  | Next PSSDC Meeting: | Thursday, Feb 28th, 2019
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSSDC Teleconference December 10th, 2018
Service to Business Community of Practice Working Group
#1B | Service to Business Working Group Co-Chairs to provide an update on the implementation of the BN Playbook at an upcoming meeting. | Anne Matthews, Pirth Singh | 2018-12-10 | Underway | Item on the February 28th agenda
PSSDC Meeting of September 27, 2018 (Whitehorse)
Service Network Collaboration Working Group
#2A | Service Network Collaboration to provide an update on the Points of Service Mapping, Service Partnership Playbook engagement Strategy and other items as per work plan. | Rob Horwood, Cheryl Meek | 2018-09-27 | Underway | Item on the February 28th agenda
#2B | Service Collaboration Working Group to provide at an upcoming teleconference suggestions on key areas of focus for a discussion on call centres at the February meeting. | Rob Horwood, Cheryl Meek | 2018-09-27 | Underway | Item on the February 28th agenda
Data Driven Intelligence Working Group
#3A | Members were asked to look at how the EVI tool could be used in their jurisdictions. Further discussion on the EVI tool to be scheduled at an upcoming teleconference or meeting. | PSSDC Members | 2018-09-27 | Pending | Item to be scheduled in Spring 2019.
#3B | Data Driven Intelligence Working Group to provide an update on the development of the DDI Playbook at an upcoming teleconference/meeting. | Guy Gordon, John Howeling | 2018-09-27 | Underway | Item on the February 28th agenda
Partnerships - Indigenous Services Canada
#4 | Hillary Thatcher, Indigenous Services Canada, to review the feedback provided by members at this meeting and to report on what are the issues across Canada for an upcoming meeting discussion. | Hillary Thatcher, Indigenous Services Canada | 2018-09-27 | Underway | Item on the February 28th agenda
Research Committee
#5 | Members requested the Joint Councils Research Committee to review the national results of CF8 and provide insights or recommendations on areas of focus (unpacking results) for PSSDC to have a meaningful conversation on this topic. | Richard Dalpé, Guy Gordon, Research Committee Co-Chairs | 2018-09-27 | Pending | ICCS has followed up with Research Committee. At their October 9th meeting, the research committee was tasked to look into this request and to report back at an upcoming teleconference in Spring 2019.
PSSDC Meeting of February 22, 2018 (Toronto)
Partnerships - Open Source
$4C | Ron Hinshaw, BC, offered to do a demo to PSSDC on BC pilot related to Open Source. (BC is currently developing tool) | Ron Hinshaw | 2018-02-22 | Underway | Item on the February 28th agenda

## Decisions
DECISIONS
| ITEM | STATUS
PSSDC TELECONFERENCE DECEMBER 10TH, 2018
#1 | PSSDC Members approved the Service to Business Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | Approval of the Terms of Reference – Mark Burns moved the approval of the terms of reference for the Data Driven Intelligence Working Group; Gillian Latham seconded. | Approved
#2 | Development of a DDI Playbook – Beverly Dicks moved the approval of development of a Data Driven Intelligence Playbook; Jackie Stankey seconded. | Approved
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC P/T Co-Chair's position: PSSDC members approved a one year extension of the P/T Co-Chair's (Natasha Clarke) position from Sept. 2018 to Sept. 2019. The P/T Co-Chair position would end at the Sept. 2019 PSSDC meeting. | Approved
#2 | Data Driven Intelligence: PSSDC members adopted a recommendation for DDI to become a priority of the PSSDC. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html