## Action Items
| PSCIOC ACTION ITEMS |  |  |  | Updated on Sept 11, 2020
|  | Next PSCIOC meeting: | September 23, 2020
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSCIOC Meeting of September 10, 2020
#1 | Create an Open Source working group to help jurisdictions with sharing projects and products with each other in open source. (focus areas: governance model, develop a guidebook, licensing model, and update and maintain the application). Working Group to report to Joint Councils. Guillaume Charest, ESDC, to lead group. Next steps: develop SoW and call out for members. | Guillaume Charest / ICCS Sec | 2020-09-10 | Pending | ICCS Secretariat to connect with Guillaume Charest to discuss the creation of the group and next steps.
PSCIOC Meeting of July 8, 2020
#1 | John O’Brien, CDS, to share via ICCS the research study related to the app and Bluetooth done by the United Kingdom. | ICCS Secretariat | 2020-07-08 | Pending | ICCS has followed up with CDS.
PSCIOC Meeting of June 11, 2020
#1A | Ari Rizvi to share with PSCIOC members: a) the analysis documents of the work that Shared Services Canada has done with Gartner; b) the operational framework for protected B for SaaS. | Ari Rizvi, Shared Services Canada | 2020-06-11 | Underway | Message sent to members on August 17th. Pending one document.
#1B | The topic of SaaS’ strategic business strategy to be discussed at an upcoming meeting | PSCIOC Members | 2020-06-11 | Pending | Agenda item for October meeting
PSCIOC Meeting of June 4, 2020
#1A | NCSIP to: · NCSIP to assist in scoping and developing a document for discussion with privacy commissioners related to ATI process and best practices around not disclosing sensitive information in response to ATI requests. . · NCSIP to engage the Canadian Centre for Cyber Security, RCMP, Privacy Commissioners and FOIP representatives to develop a Pan-Canadian drill re malware and incident response. | NCSIP Chair | 2020-06-04 | Underway | Agenda item on the PSCIOC september meeting -prep discussion on Aug 26th
#1B | Future topics for discussion at upcoming PSCIOC Meetings: · Emerging threats and risks; · Is your security team right sized for your organization? -How well is your security team linked to IT / cyber operations? | PSCIOC Members | 2020-06-04 | Pending | Agenda Item on a future PSCIOC meeting
PSCIOC Meeting of May 21, 2020
#1B | Po Tea-Duncan to share with PSCIOC members the guide that they developed for Cloud back up solutions and incidents. | Po Tea-Duncan, TBS | 2020-05-21 | Pending | Po Tea-Duncan advised that the guide is a work in progress and when available, will be shared with members
PSCIOC Meeting of April 17, 2020
#1A | Cloud: Dan Cooper, Cloud Community of Practice Chair to share the journey map on cost benefit with the PSCIOC members when finalized. | Cloud CoP Chair | 2020-04-17 | Pending | ICCS followed up with Dan Cooper.

## Decisions
DECISIONS
| ITEM | STATUS
PSCIOC MEETING OF JUNE 4 2020
#1 | PSCIOC Members agreed on moving from weekly PSCIOC meeting to bi-weekly meetings until further notice. | Approved
PSCIOC MEETING OF MAY 21 2020
#1 | PSCIOC Members approved Zelko Holjevac as the new Lead of the Microsoft Office 365 group. | Approved
PSCIOC MEETING OF APRIL 24 2020
#1 | PSCIOC members decided to invite the PSSDC members at their April 30th meeting to discuss the Business Resumption Planning. | Approved
PSCIOC MEETING OF MARCH 24, 2020
#1 | Members approved the decision of weekly PSCIOC meetings to discuss the work during the COVID-19 pandemic. | Approved
PSCIOC MEETING OF FEBRUARY 26, 2020
#1 | Record of Decision of September 26, 2019, PSCIOC meeting in Winnipeg approved without changes. | Approved
#2 | Agenda of February 26th, 2020 PSCIOC meeting approved. | Approved
#3 | CJ Ritchie moved that the Data Driven Intelligence (DDI) Group be moved to the Joint Councils; seconded Natasha Clarke. | Approved
#4 | Catherine Desgagnés-Belzil moved that the Service to Business Working Group be moved to the Joint Councils; seconded Natasha Clarke. | Approved
PSCIOC TELECONFERENCE OF JANUARY 17, 2020
#1 | PSCIOC members were in support of adopting recommendation #3 to adjust the PSCIOC annual contributions to a phased-in approach. Adjustment would take effect starting fiscal period 2020-2021. | Approved
PSCIOC MEETING OF SEPTEMBER 26, 2019 (WINNIPEG)
#1 | Record of Decision of February 28th, 2019, PSCIOC meeting in Ottawa approved without changes. | Approved
#2 | Agenda of September 26th, 2019 PSCIOC meeting approved. | Approved
PSCIOC TELECONFERENCE OF AUGUST8, 2019
#1 | Record of Decision from June 10 Teleconference were approved | Approved
#1 | PSCIOC Members confirmed Tracy Wood as the new PSCIOC Co-Chair, starting on June 1st, 2019. | Approved
#2 | PSCIOC Members confirmed Bonnie Schmidt as the new PSCIOC Treasurer starting in August 2019. | Approved
#3 | PSCIOC Members approved the Cloud Working Group Workplan and updated Terms of Reference with requested amendment. | Approved
PSCIOC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | As FPTM CIOs, we agree to go to our own jurisdiction and deal with the http issue (moving to https). Jurisdictions can use the federal tools available. Members to advise their jurisdiction that this was brought up by NCSIP and we need to take action to clean this up. NCSIP to track the inventories and progress as part of the artifacts they are collecting. | Approved
#2 | PSCIOC members agreed for MISA to be able to share information from the jurisdictional information sharing collected for each in person meeting, however confidential information (or what is considered sensitive information) can only be shared if the jurisdictional member (author) is consulted and approval is given to share. | Approved
PSCIOC MEETING OF FEBRUARY 22, 2018
#1 | PSCIOC members approved the request by NCSIP to fund four day meetings twice a year, up to a maximum of 8 meeting days per year. (The current policy only allows up to a maximum of 6 meeting days per year.) This approval only applies to NCSIP and not to other groups of PSCIOC. | Approved
#2 | NCSIP: General agreement (access and support) in principle by members on all the recommendations by NCSIP. | Approved
#3 | Information Management (IM) Sub-Committee - Framework Working Group recommended for the IM Sub-Committee to transition to a Community of Practice. PSCIOC members agreed to keep group as is for now and to have a further discussion on potential areas of work for this group. PSCIOC members also agreed to discuss with their jurisdictional colleagues in this space to identify areas of work that can be tasked to the IM Sub-Committee. PSCIOC members to have a further discussion on this matter at an upcoming teleconference. | Approved
#4 | Information and Communication Technology Policy Working Group - Framework Working Group recommended for the ICT Policy Working Group to transition to a Community of Practice. PSCIOC members agreed to reach out to ICT Policy Working Group Co-Chairs and get a better understanding of their current work and identify areas of potential collaboration and support in order to determine next steps. PSCIOC members to have a further discussion on this item at an upcoming teleconference. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html