## Action Items
| PSSDC ACTION ITEMS |  |  |  | Last updated: Sept 11, 2020
|  | Next PSSDC Meeting | Thursday, Sept. 24, 2020
| ACTION ITEM | LEADS | DATE ASSIGNED | STATUS | NOTES
PSSDC Meeting of September 3rd, 2020
#1A | PSSDC Co-Chairs to clarify the relationship between the FPT DMs’ Table and PSSDC, by improving communication and share information from the top down and report back to a future PSSDC meeting. | PSSDC Co-Chairs | 2020-09-03 | Pending
#1B | ICCS to provide suggestions on how best to take the PSSDC info sharing reports and create a summary or searchable document highlighting the emergent topics, tagging common initiatives into specific categories and how to create business intelligence for the clients and create ways that bring immediate value and insights to the Councils. | ICCS | 2020-09-03 | Pending | ICCS to provide recommendations at an upcoming meeting in fall 2020
PSSDC Meeting of February 26th, 2020 (Toronto)
Adminstrative Matters
| A further discussion on the PSSDC finances was requested for a future teleconference. | PSSDC Treasurer | 2020-02-26 | Underway | Financial report on the september agenda
Service to Business Working Group
#1B | Service to Business Working Group to develop the work plan and present it to the PSSDC at the next teleconference. | Service to Business WG Co-Chairs | 2020-02-26 | Underway | Members made a decision was made to move S2B WG under JC. Next update from the group will be tabled at JC.
| Service to Business Working Group to send a call for participation to members via ICCS. | Service to Business WG Co-Chairs | 2020-02-26
#2A | Service to Business Working Group to send the request for funding with the Scope of Work to the PSSDC Co-Chairs for analysis and approval. | Service to Business WG Co-Chairs | 2020-02-26
#2B | Services to Indigenous Populations
#2C | Further discussion on the Services to Indigenous Populations to be included on the agenda for the next in-person meeting. | Indigenous Services Canada Member | 2020-02-26 | Underway | Item on the September meeting agenda
Contact Centre Community of Practice
#3A | Contact Centre Community of Practice to present the Terms of Reference for approval at the next PSSDC teleconference. | Contact Centre Community of Practice Co-Chairs | 2020-02-26 | Pending | For follow up in Fall 2020
PSSDC Meeting of September 26, 2019 (Winnipeg)
#4 | Best Practices Showcase (IRCC - Measuring the Impact of Service Design Changes)
| IRCC invited to provide a progress report at an upcoming meeting on their work/results related to measuring the impact of service design changes. | PSSDC Member representing IRCC | 2019-09-26 | Pending | For follow up in November 2020.
PSSDC Meeting of September 27, 2018 (Whitehorse)
#4 | Research Committee
| Members requested the Joint Councils Research Committee to review the national results of CF8 and provide insights or recommendations on areas of focus (unpacking results) for PSSDC to have a meaningful conversation on this topic. | Richard Dalpé, Guy Gordon, Research Committee Co-Chairs | 2018-09-27 | Pending | ICCS has followed up with Research Committee. The Research Committee to follow up on this at an upcoming meeting/teleconference.
#5

## Decisions
DECISIONS
| ITEM | STATUS
PSSDC MEETING OF SEPTEMBER 3, 2020
#1 | Members agreed to move the Service to Business under the Joint Councils, with the note that PSSDC will provide direction to the group on future activities. | Approved
PSSDC MEETING OF FEBRUARY 26, 2020
#1 | The Record of Decision from the PSSDC September 26th, 2019 meeting has been approved without changes. | Approved
#2 | The PSSDC February 26th, 2020 meeting agenda has been approved without changes. | Approved
PSSDC TELECONFERENCE OF NOVEMBER 15, 2019
#1 | PSSDC members approved the updated Service to Business Working Group Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 26, 2019
#1 | The Record of Decision from the PSSDC February 28th, 2019 meeting approved without changes. | Approved
#2 | The PSSDC September 26th, 2019 meeting agenda approved without changes. | Approved
#3 | PSSDC Members approved recommendation from the Service to Business Working Group to amend its Terms of Reference to include a second P/T Co-Chair. | Approved
#4 | PSSDC members approved Mark Burns as incoming P/T Co-Chair. The term of the P/T co-chair is for a period of two years. | Approved
PSSDC MEETING OF FEBRUARY 28, 2019
#1 | The Record of Decision from September 27th, 2018 PSSDC meeting in Whitehorse approved without changes. | Approved
#2 | The February 28th, 2019 PSSDC meeting agenda approved without changes. | Approved
#3 | The Service Network Collaboration Working Group to be sunset. | Approved
PSSDC TELECONFERENCE DECEMBER 10TH, 2018
#1 | PSSDC Members approved the Service to Business Terms of Reference. | Approved
PSSDC MEETING OF SEPTEMBER 27, 2018 (WHITEHORSE)
#1 | Approval of the Terms of Reference – Mark Burns moved the approval of the terms of reference for the Data Driven Intelligence Working Group; Gillian Latham seconded. | Approved
#2 | Development of a DDI Playbook – Beverly Dicks moved the approval of development of a Data Driven Intelligence Playbook; Jackie Stankey seconded. | Approved
PSSDC MEETING OF FEBRUARY 22, 2018
#1 | PSSDC P/T Co-Chair's position: PSSDC members approved a one year extension of the P/T Co-Chair's (Natasha Clarke) position from Sept. 2018 to Sept. 2019. The P/T Co-Chair position would end at the Sept. 2019 PSSDC meeting. | Approved
#2 | Data Driven Intelligence: PSSDC members adopted a recommendation for DDI to become a priority of the PSSDC. | Approved

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html